|  |  |  |  |
| --- | --- | --- | --- |
| **To,**  **Prof. Juerg M. Matter**  Project Director, ODP | | ***Doc. No.:*** *AZD/ODP/GT-1A/DPR-40*  ***Dated:*** *02-02-2017* | |
| **Client** | Oman DP | **Consultant** | AZD Engineering Consultancy |
| **Contractor** | Lalbuksh Voltas Engineering | **Sub-contractor** | Geo-Solutions Engineering |
| **Subject** | Daily Progress Report |  | |
| **Project** | **Phase-1: OmanDP -** Scientific Drilling Programme for Oman Drilling Project in Ash Sharqiyah North Governorate and Ad Dakhiliyah Governorate | | |

**DAILY PROGRESS REPORT**

**(Dated: 2nd of February 2017)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Rig-1 (Dynatech)** | | | |
| ***LOCATION AND TARGET:*** | | | |
| **Drill Hole ID** | **GT-1A** | **Location** | Wadi Gideah |
| **Coordinates** | UTM: E655373.7 N2532417.3 | **Elevation** | **-** |
| **Azimuth** | **-** | **Inclination** | 90º/ Vertical |
| **Drilling** | HQ Size | **Method** | Wire line-Diamond Core Drilling |
| **Target Depth** | 400 mtrs | **Geol. Target** | Gabbro-Hydrothermal Fault Zone |
| ***DRILLING:*** | | | |
| **Drilling Status** | PooH HQ drill assembly and installed NC casing. RIH NQ drill assembly and started drilling with NQ drill bit from 251.7mbgl and drilled up to 255.80 mbgl. | | |
| **Penetration Rate** | Variable; 45 min/core of 3 meter | | |
| **Bit Rotation** | Variable; Average 450 rpm | | |
| **Fluid Circulation** | 60%; Partial loss circulation | | |
| **Total Drill Run** | 3; being of 1.10, 2.8 and 0.2 meters each | | |
| **Today’s Drilling** | **4.10m** | | |
| **Cumulative Total** | **255.80m** | | |
| ***CORE CURATION:*** | | | |
| **Core Recovery, Photography, Marking, Sectioning, Scanning, Labeling, Sketching, Description, Sampling, Packing and Storage etc., being performed as per the standard procedure of ICDP.**  **Brief Lithology: Ophiolite consisting of Gabbro litho unit mostly greenish to olivine rich at places, moderately strong, fresh to altered, foliated to compact gabbro; presence of veins and veinlet of siliceous hydrothermal alteration products mixed with gypsum.** | | | |
| ***PERSONNEL ONSITE:*** | | | |
| **ODP :** Jude Coggon, Anna Jesus, Nicholas Bompard, Gretchen Bernasconi-Green, [Michelle Harris](https://twitter.com/michelleharri5)  **AZD :** Nehal H Warsi  **LBV :** Gopi Krishnan  **GSE :** Sheikh Olliullah (D); Abdul Khaliq, Mohd. Jameel, Mohd. Alauddin  **Others:** | | | |
| ***REMARKS:*** | | | |
| ***Difference in the length of HQ and NQ drill pipes adjusted after the installation.*** | | | |

Best Regards,

**Nehal H Warsi**

# *Site Geologist, AZD Engineering Consultancy*

**GSM: +968 98037217; 79113454**

**Email: nhwarsi@gmail.com**