|  |  |  |  |
| --- | --- | --- | --- |
| **To,**  **Prof. Juerg M. Matter**  Project Director, ODP | | ***Doc. No.:*** *AZD/ODP/GT-1A/DPR-31*  ***Dated:*** *24-01-2017* | |
| **Client** | Oman DP | **Consultant** | AZD Engineering Consultancy |
| **Contractor** | Lalbuksh Voltas Engineering | **Sub-contractor** | Geo-Solutions Engineering |
| **Subject** | Daily Progress Report |  | |
| **Project** | **Phase-1: OmanDP -** Scientific Drilling Programme for Oman Drilling Project in Ash Sharqiyah North Governorate and Ad Dakhiliyah Governorate | | |

**DAILY PROGRESS REPORT**

**(Dated: 24th of January 2017)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Rig-1 (Dynatech)** | | | |
| ***LOCATION AND TARGET:*** | | | |
| **Drill Hole ID** | **GT-1A** | **Location** | Wadi Gideah |
| **Coordinates** | UTM: E655373.7 N2532417.3 | **Elevation** | **-** |
| **Azimuth** | **-** | **Inclination** | 90º/ Vertical |
| **Drilling** | HQ Size | **Method** | Wire line-Diamond Core Drilling |
| **Target Depth** | 400 mtrs | **Geol. Target** | Gabbro-Hydrothermal Fault Zone |
| ***DRILLING:*** | | | |
| **Drilling Status** | Continued drilling with HQ drill bit from 17.7mbgl and stopped at 41.7mbgl. | | |
| **Penetration Rate** | Variable; Between 40-50 min/core of 3 mtr | | |
| **Bit Rotation** | Variable; Average 350 rpm | | |
| **Fluid Circulation** | 80%; Normal circulation | | |
| **Total Drill Run** | 8; all being of 3 meters each | | |
| **Today’s Drilling** | **24.00m** | | |
| **Cumulative Total** | **41.70m** | | |
| ***CORE CURATION:*** | | | |
| **Core Recovery, Photography, Marking, Sectioning, Scanning, Labeling, Sketching, Description, Sampling, Packing and Storage etc., being performed as per the standard procedure of ICDP.**  **Brief Lithology: Ophiolite consisting of Gabbro litho unit mostly olivine rich; medium to coarse grained greenish gray to gray, moderately strong to strong fresh then at times highly fractured, oxidized showing dark spotted foliations at some intervals; altered at places foliated to layered gabbro with less; Presence of veins and veinlet of siliceous hydrothermal alteration products mixed with carbonates** | | | |
| ***PERSONNEL ONSITE:*** | | | |
| **ODP :** Jude Coggon, Benoit Ildefonse, Anna Jesus, Samuel Mueller  **AZD :** Nehal H Warsi  **LBV :** Gopi Krishnan  **GSE :** Sheikh Olliullah (D); Abdul Khaliq, Mohd. Jameel, Alauddin | | | |
| ***REMARKS:*** | | | |
| ***\*Pleasant weather all day; Drilling activity was stopped before evening @3:45 pm because of some rain.***  ***\*A total of 119 HQ/NQ core boxes from GT-2A transported to Muscat.*** | | | |

Best Regards,

**Nehal H Warsi**

*Site Geologist, AZD Engineering Consultancy*

**GSM: +968 98037217; 79113454**

**Email: nhwarsi@gmail.com**