|  |  |
| --- | --- |
| **To,** **Prof. Juerg M. Matter** Project Director, ODP | ***Doc. No.:*** *AZD/ODP/GT-1A/DPR-33****Dated:*** *26-01-2017* |
| **Client** | Oman DP | **Consultant** | AZD Engineering Consultancy |
| **Contractor** | Lalbuksh Voltas Engineering | **Sub-contractor** | Geo-Solutions Engineering |
| **Subject**  | Daily Progress Report |  |
| **Project** | **Phase-1: OmanDP -** Scientific Drilling Programme for Oman Drilling Project in Ash Sharqiyah North Governorate and Ad Dakhiliyah Governorate |

**DAILY PROGRESS REPORT**

**(Dated: 26th of January 2017)**

|  |
| --- |
| **Rig-1 (Dynatech)** |
| ***LOCATION AND TARGET:*** |
| **Drill Hole ID** | **GT-1A**  | **Location** | Wadi Gideah |
| **Coordinates** | UTM: E655373.7 N2532417.3 | **Elevation** | **-** |
| **Azimuth** | **-** | **Inclination** | 90º/ Vertical |
| **Drilling** | HQ Size | **Method** | Wire line-Diamond Core Drilling |
| **Target Depth**  | 400 mtrs | **Geol. Target** | Gabbro-Hydrothermal Fault Zone |
| ***DRILLING:*** |
| **Drilling Status**  | Continued drilling with HQ drill bit from 62.7mbgl and drilled up to 95.7mbgl.  |
| **Penetration Rate**  | Variable; Between 30-70 min/core of 3 meter |
| **Bit Rotation**  | Variable; Average 350 rpm |
| **Fluid Circulation**  | 80%; Normal circulation |
| **Total Drill Run**  | 13; 9 being of 3 meters and 4 others being of 0.2, 2.8, 2.5 and 0.5m each |
| **Today’s Drilling**  | **33.00m *(Highest meterage in a single day so far, of the project)*** |
| **Cumulative Total**  | **95.70m**  |
| ***CORE CURATION:*** |
| **Core Recovery, Photography, Marking, Sectioning, Scanning, Labeling, Sketching, Description, Sampling, Packing and Storage etc., being performed as per the standard procedure of ICDP.****Brief Lithology: Ophiolite consisting of Gabbro litho unit mostly olivine rich; medium to coarse grained at places large crystals, greenish gray to dark gray, moderately strong to strong fresh then at times fractured, oxidized showing dark spotted foliations at some intervals; altered at places foliated to layered gabbro and plagioclase bands; Presence of veins and veinlet of siliceous hydrothermal alteration products mixed with carbonates in fractures; Many small sheared fault zones and a big fault zone between 83.4 to 86.75m and presence of wehrlite towards the end.** |
| ***PERSONNEL ONSITE:*** |
| **ODP :** Jude Coggon, Benoit Ildefonse, Anna Jesus, Nicholas Bompard**AZD :** Nehal H Warsi**LBV :** Gopi Krishnan**GSE :** Sheikh Olliullah (D); Abdul Khaliq, Mohd. Jameel, Alauddin |
| ***REMARKS:***  |
| ***\* The drill permit for GT-3 has been obtained by the contractor.*** ***\* Drilling will continue tomorrow on Friday.*** |

Best Regards,

**Nehal H Warsi**

*Site Geologist, AZD Engineering Consultancy*

**GSM: +968 98037217; 79113454**

**Email: nhwarsi@gmail.com**