| To: | Prof. Juerg M. Matter Project Director, Oman Drilling Project | Doc. No.: AZD/ODP/GT-2A/DPR-23 Dated: 16-01-2017 |
| --- | --- | --- |
| Client : | Oman DP | Consultant : AZD Engineering Consultancy |
| Contractor : | Lalbuksh Voltas | Sub-contractor: Geo-Solutions Engineering |
| Subject : Daily Progress Report |
| Project : Phase-1: OmanDP - Scientific Drilling Programme for Oman Drilling Project in Ash Sharqiyah North Governorate and Ad Dakhiliyah Governorate |

DAILY PROGRESS REPORT

(Dated: 16th of January 2017)

Rig-1 (Dynatech)

LOCATION AND TARGET:

Drill Hole ID : GT-2A Location : Wadi Gideah Coordinates : UTM: E655960.7 N2529193.5 Azimuth : 54 ºN; Inclination : 60º Drilling : HQ/NQ Size; Method : Wire line-Diamond Core Drilling Target Depth : 400 mtrs Geol. Target : Gabbro-Transition from Foliated to Layered

DRILLING:

Drilling Status : Continue drilling with NQ size diamond drill bit from 356.4mbgl and drilled up to 377.4mbgl. Penetration Rate : Variable; between 40-55 minutes Bit Rotation : Variable; between 100-120 rpm Fluid Circulation : 20%; Huge Loss Total Drill Run : 07; All being of 3m length; Today’s Drilling : 21 m; Cumulative Total : 377.4 m (HQ=149.7m; NQ=227.7 m)

CORE CURATION:

Core Recovery, Photography, Marking, Scanning, Labeling, Sketching, Description, Sampling, and Storage etc. being performed as per the standard procedure. Brief Lithology: Ophiolite mostly consisting of massive Gabbro litho unit; medium to coarse grained greenish gray to gray, moderately strong to strong at times highly fractured and sheared showing dark spotted foliations at some intervals; little to highly altered at places, chlorite alterations with some ultramafic bands of dark green to black wehrlite showing presence of crystals and patches of pyrite into it; Presence veins and veinlet of siliceous hydrothermal alteration products

OTHER ISSUES:

Contractual Issues : None Technical Issues : None Health & Safety Issues: None Logistic Issues : Availability of Core boxes and Cover: Shipment Arrives in Muscat.

Remarks : Water tanker of the 5000 Gallons capacity made available by Geo-Solutions.

Regards,

Nehal H Warsi

Site Geologist, AZD Engineering Consultancy

GSM:  +968 98037217; 79113454

Email: nhwarsi@gmail.com