| To: | Prof. Juerg M. Matter Project Director, Oman Drilling Project | Doc. No.: AZD/ODP/GT-2A/WR-02 Dated : 07/01/2017 |
| --- | --- | --- |
| Client : | Oman DP | Consultant : AZD Engineering Consultancy |
| Contractor: | Lalbuksh-Voltas | Sub-contractor: Geo-Solutions Engineering |
| Subject : Weekly Progress Report |
| Project : Phase-1: OmanDP - Scientific Drilling Programme for Oman Drilling Project in Ash Sharqiyah North Governorate and Ad Dakhiliyah Governorate |

WEEKLY PROGRESS REPORT-02

(1st -7th of January 2017)

Weekly Summary:

|  | DH ID | LOCATION | RIG ID | CORE SIZE | DATE | DRILLING | AVERAGE DRILLING (Meters/Day) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WEEK |  |  |  |  | FROM | TO | HQ (m) | NQ (m) |  |
| 01 | GT-2A | Wadi Gideah | Rig-1 | HQ | 25-12-16 | 31-12-16 | 115.40 | - | 16.40 |
| 02 | GT-2A | Wadi Gideah | Rig-1 | HQ/NQ | 01-01-17 | 07-01-17 | 34.30 | 47.70 | 11.70 |
| TOTAL | 149.70 | 47.70 |  |

Week: 02

| DATE | DAYS | DRILLING | TOTAL DRILLING | CORE SIZE | REMARKS |
| --- | --- | --- | --- | --- | --- |
|  |  | From (m) | To (m) | (m) | (HQ/NQ) |  |
| 01-01-2017 | Sunday | 115.40 | 137.40 | 22.00 | HQ | Total loss of circulation |
| 02-01-2017 | Monday | 137.40 | 149.40 | 12.00 | HQ | 1. Total loss of circulation is continued; So, Driller asked for NQ size to drill further; 2. Breakdown: Engine heating problem; Tried to fix; Operation stopped from 10:15 AM- 2:15 PM. |
| 03-01-2017 | Tuesday | 149.40 | 149.70 | 0.30 | HQ | Total loss of circulation continued; Decided to drill further with NQ size. Drill assembly POOH. RIH HQ drill pipes with shoe bit up to 149.7m. Lowered in hole the drill assembly with NQ size diamond drill bit. |
| 04-01-2017 | Wednesday | - | - | - | - | Preparations made for the drilling with NQ but HQ-NQ adapter not fixed. Trying to fix the problem. waiting; No drilling |
| 05-01-2017 | Thursday | - | - | - | - | Drill bit and core barrel not matching; trying to fix the problem; waiting; No drilling |
| 06-01-2017 | Friday | 149.70 | 170.40 | 20.70 | NQ | Drilling with NQ size diamond drill bit; Circulation starts again. |
| 07-01-2017 | Saturday | 170.40 | 197.4 | 27.00 | NQ | Continue drilling; Circulation contd. |

Other Problem: Issue of Core boxes and core box cover still not solved.

Regards,

Nehal H Warsi

Site Geologist, AZD Engineering Consultancy

GSM:  +968 98037217; 79113454

Email: nhwarsi@gmail.com