| To: | Prof. Juerg M. Matter Project Director, Oman Drilling Project | Doc. No.: AZD/ODP/GT-2A/WR-01 Dated : 31/12/2016 |
| --- | --- | --- |
| Client : | Oman DP | Consultant : AZD Engineering Consultancy |
| Contractor: | Lalbuksh-Voltas | Sub-contractor: Geo-Solutions |
| Subject : Weekly Progress Report |
| Project : Phase-1: OmanDP - Scientific Drilling Programme for Oman Drilling Project in Ash Sharqiyah North Governorate and Ad Dakhiliyah Governorate |

WEEKLY PROGRESS REPORT-01

(25th -31st of December 2016)

Weekly Summary:

| DRILL HOLE ID | LOCATION | RIG ID | CORE SIZE | DATE | DRILLING | AVERAGE DRILLING (Meters/Day) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | START | COMPLETION | FROM (m) | TO (m) |  |
| GT-2A | Wadi Gideah | Rig-1 | HQ | 25-12-2016 | In Progress | GL/0.00 | 115.40 | 16.40 |

Week: 01

| DATE | DAYS | DRILLING | TOTAL DRILLING | CORE SIZE | REMARKS |
| --- | --- | --- | --- | --- | --- |
|  |  | From (m) | To (m) | (m) | (HQ/NQ) |  |
| 25-12-2016 | Sunday | GL/0.00 | 7.40 | 7.40 | HQ | START of Drilling |
| 26-12-2016 | Monday | 7.40 | 9.60 | 2.20 | HQ | Total loss of circulation; Reaming and installation of surface casing (6m). Drill fluid injector hose got twisted and leaking; Repaired |
| 27-12-2016 | Tuesday | 9.60 | 29.40 | 19.80 | HQ | Total loss of circulation. |
| 28-12-2016 | Wednesday | 29.40 | 53.40 | 24.00 | HQ | Total loss of circulation. Minor Leakage at rear of control panel-fixed; Drilling stopped at 3:50 PM because of the non-availability of drilling water-Water tanker’s Tyre burst midway near site |
| 29-12-2016 | Thursday | 53.40 | 80.40 | 27.00 | HQ | Total loss of circulation. |
| 30-12-2016 | Friday | 80.40 | 92.40 | 12.00 | HQ | Total loss of circulation. *Drilling only up to 11:30 AM; Crew moved for Friday Prayers. |
| 31-12-2016 | Saturday | 92.40 | 115.4 | 23.00 | HQ | Total loss of circulation. |

Regards,

Nehal H Warsi

Site Geologist,

AZD Engineering Consultancy

GSM:  +968 98037217; 79113454

Email: nhwarsi@gmail.com

Cc to:

Sydney De Silva: sydneysdesilva@gmail.com, Mazin Al Suleimani: adrtoman@gmail.com,

Zaher Al Suleimani: zahrslmn@omantel.net.com