## Operation Summary
Expedition 335 Operation Summary, based on R. Grout (Operations Superintendent) daily operations reports
Time breakdown is by nearest 1/4 hour |  |  |  |  | Expedition (from departure time) | [5 empty] | On Site
| Start |  | End |  | Duration |  |  | Time (cumulative) |  |  | Duration |  |  | Time (cumulative)
Operation | local time (h) | Date (2011) | local time (h) | Date (2011) | (mn) | (h) | (days) | (mn) | (h) | (days) | (mn) | (h) | (days) | (mn) | (h) | (days) | comments
In Puntarenas for Port Call activities |  | 2011-04-14 | 4:30 | 2011-04-17 | [12 empty] | Beginning of Expedition 335
Depart Puntarenas, and transit to Site 1256 | 4:30 | 2011-04-17 | 1:15 | 2011-04-19 | 2685 | 44.75 | 1.8646 | 2685 | 44.75 | 1.8646 | [6 empty] | 11.3 knots @ April 18, 06:30
On position at Hole 1256D. Pick up mouse hole, make up BHA with tricone bit and MBR. Run in with the drillstring while measuring and rabbiting all tubulars to 2733 mbrf. | 1:15 | 2011-04-19 | 10:15 | 2011-04-19 | 540 | 9 | 0.375 | 3225 | 53.75 | 2.2396 | 540 | 9 | 0.375 | 540 | 9 | 0.375 | Start Run 1. Smith 9 7/8” F9 tricone bit
Launch VIT | 10:15 | 2011-04-19 | 11:00 | 2011-04-19 | 45 | 0.75 | 0.03125 | 3270 | 54.5 | 2.2708 | 45 | 0.75 | 0.03125 | 585 | 9.75 | 0.40625
RIH with the drillstring from 2733 to 3246 mbrf | 11:00 | 2011-04-19 | 12:15 | 2011-04-19 | 75 | 1.25 | 0.052083 | 3345 | 55.75 | 2.3229 | 75 | 1.25 | 0.052083 | 660 | 11 | 0.45833
Lose VIT signal. Retrieve VIT and repair cable head. Redeploy VIT | 12:15 | 2011-04-19 | 15:30 | 2011-04-19 | 195 | 3.25 | 0.13542 | 3540 | 59 | 2.4583 | 195 | 3.25 | 0.13542 | 855 | 14.25 | 0.59375
RIH with the drillstring from 3246 to 3637 mbrf | 15:30 | 2011-04-19 | 17:30 | 2011-04-19 | 120 | 2 | 0.083333 | 3660 | 61 | 2.5417 | 120 | 2 | 0.083333 | 975 | 16.25 | 0.67708
Search and position vessel for reentry. Reenter Hole 1256D at 1800 hr | 17:30 | 2011-04-19 | 18:00 | 2011-04-19 | 30 | 0.5 | 0.020833 | 3690 | 61.5 | 2.5625 | 30 | 0.5 | 0.020833 | 1005 | 16.75 | 0.69792 | Reentry 1
Continue to RIH to 258.8 mbsf | 18:00 | 2011-04-19 | 19:15 | 2011-04-19 | 75 | 1.25 | 0.052083 | 3765 | 62.75 | 2.6146 | 75 | 1.25 | 0.052083 | 1080 | 18 | 0.75
Recover VIT | 19:15 | 2011-04-19 | 20:00 | 2011-04-19 | 45 | 0.75 | 0.03125 | 3810 | 63.5 | 2.6458 | 45 | 0.75 | 0.03125 | 1125 | 18.75 | 0.78125
Continue to RIH with 5 ½ inch drillpipe to 925.0 mbsf where formation took 25 Kips. Cancel attempt to obtain temperature log and water sample | 20:00 | 2011-04-19 | 21:45 | 2011-04-19 | 105 | 1.75 | 0.072917 | 3915 | 65.25 | 2.7187 | 105 | 1.75 | 0.072917 | 1230 | 20.5 | 0.85417
Pull back in the hole from 925.0 to 891.9 mbsf | 21:45 | 2011-04-19 | 22:00 | 2011-04-19 | 15 | 0.25 | 0.010417 | 3930 | 65.5 | 2.7292 | 15 | 0.25 | 0.010417 | 1245 | 20.75 | 0.86458 | Obstruction
Pick up 20-foot knobby and top drive | 22:00 | 2011-04-19 | 22:45 | 2011-04-19 | 45 | 0.75 | 0.03125 | 3975 | 66.25 | 2.7604 | 45 | 0.75 | 0.03125 | 1290 | 21.5 | 0.89583
Run in with the top drive to 920.0 mbsf | 22:45 | 2011-04-19 | 23:30 | 2011-04-19 | 45 | 0.75 | 0.03125 | 4020 | 67 | 2.7917 | 45 | 0.75 | 0.03125 | 1335 | 22.25 | 0.92708
Work pipe at 920-925 mbsf which is the depth where we had hole problems on Exp 312. Erratic torque with TD current = 500 amps. | 23:30 | 2011-04-19 | 1:15 | 2011-04-20 | 105 | 1.75 | 0.072917 | 4125 | 68.75 | 2.8646 | 105 | 1.75 | 0.072917 | 1440 | 24 | 1
Pull back from 920 to 891.5 mbsf | 1:15 | 2011-04-20 | 1:30 | 2011-04-20 | 15 | 0.25 | 0.010417 | 4140 | 69 | 2.875 | 15 | 0.25 | 0.010417 | 1455 | 24.25 | 1.0104
Change out swivel packing | 1:30 | 2011-04-20 | 2:45 | 2011-04-20 | 75 | 1.25 | 0.052083 | 4215 | 70.25 | 2.9271 | 75 | 1.25 | 0.052083 | 1530 | 25.5 | 1.0625
Resume washing and reaming from 891.5 to 923.3 mbsf. Work stuck pipe from 0415 to 0515 hr when rotation was lost. Unable to apply more than 10 Kips WOB without stalling top drive. Circulate a total of 600 bbl of hi-vis gel during the 24-hour period. Unable to work penetrate deeper than 923.3 mbsf. Pump 150 bbl sweep at 923.3 mbsf. Decide to trip the drillstring to change to a tricone bit with a more aggressive cutting structure. | 2:45 | 2011-04-20 | 6:00 | 2011-04-21 | 1635 | 27.25 | 1.1354 | 5850 | 97.5 | 4.0625 | 1635 | 27.25 | 1.1354 | 3165 | 52.75 | 2.1979
POOH with the top drive from 923.3 to 833.9 mbsf | 6:00 | 2011-04-21 | 6:45 | 2011-04-21 | 45 | 0.75 | 0.03125 | 5895 | 98.25 | 4.0937 | 45 | 0.75 | 0.03125 | 3210 | 53.5 | 2.2292
Rack top drive | 6:45 | 2011-04-21 | 7:15 | 2011-04-21 | 30 | 0.5 | 0.020833 | 5925 | 98.75 | 4.1146 | 30 | 0.5 | 0.020833 | 3240 | 54 | 2.25
POOH from 833.9 mbsf and clear sea floor at 0900 hr. Rack four stands of drill collars in derrick. Lay out MBR, LSS, MTS, and MHS. Bit clears rotary at 1550 hr. | 7:15 | 2011-04-21 | 15:45 | 2011-04-21 | 510 | 8.5 | 0.35417 | 6435 | 107.25 | 4.4687 | 510 | 8.5 | 0.35417 | 3750 | 62.5 | 2.6042 | Clear seafloor at 09:00. End Run 1 at 15:50.
Make up new Reed 9 7/8” tricone, bit sub with float valve, and tandem set of boot baskets. RIH with the drillpipe to 2877 mbrf | 15:45 | 2011-04-21 | 22:30 | 2011-04-21 | 405 | 6.75 | 0.28125 | 6840 | 114 | 4.75 | 405 | 6.75 | 0.28125 | 4155 | 69.25 | 2.8854 | Start Run 2. Reed 9 7/8” tricone bit (IADC Type 517) + Boot Baskets
Deploy VIT | 22:30 | 2011-04-21 | 23:15 | 2011-04-21 | 45 | 0.75 | 0.03125 | 6885 | 114.75 | 4.7812 | 45 | 0.75 | 0.03125 | 4200 | 70 | 2.9167
Resume RIH with the drillstring to 3638 mbrf | 23:15 | 2011-04-21 | 0:45 | 2011-04-22 | 90 | 1.5 | 0.0625 | 6975 | 116.25 | 4.8437 | 90 | 1.5 | 0.0625 | 4290 | 71.5 | 2.9792
Position vessel and reenter Hole 1256D at 0105 hr | 0:45 | 2011-04-22 | 1:15 | 2011-04-22 | 30 | 0.5 | 0.020833 | 7005 | 116.75 | 4.8646 | 30 | 0.5 | 0.020833 | 4320 | 72 | 3 | Reentry 2
RIH to 259.3 mbsf | 1:15 | 2011-04-22 | 1:30 | 2011-04-22 | 15 | 0.25 | 0.010417 | 7020 | 117 | 4.875 | 15 | 0.25 | 0.010417 | 4335 | 72.25 | 3.0104
Retrieve and recover VIT | 1:30 | 2011-04-22 | 2:30 | 2011-04-22 | 60 | 1 | 0.041667 | 7080 | 118 | 4.9167 | 60 | 1 | 0.041667 | 4395 | 73.25 | 3.0521
Resume RIH from 259.3 to 892.1 mbsf | 2:30 | 2011-04-22 | 4:15 | 2011-04-22 | 105 | 1.75 | 0.072917 | 7185 | 119.75 | 4.9896 | 105 | 1.75 | 0.072917 | 4500 | 75 | 3.125
Pick up top drive | 4:15 | 2011-04-22 | 4:45 | 2011-04-22 | 30 | 0.5 | 0.020833 | 7215 | 120.25 | 5.0104 | 30 | 0.5 | 0.020833 | 4530 | 75.5 | 3.1458
Wash and ream hole from 892.1. Attempt to pass bridge at ~920 mbsf. Pump 50-bbl hivis mud sweep | 4:45 | 2011-04-22 | 6:30 | 2011-04-22 | 105 | 1.75 | 0.072917 | 7320 | 122 | 5.0833 | 105 | 1.75 | 0.072917 | 4635 | 77.25 | 3.2187
Work stuck pipe | 6:30 | 2011-04-22 | 7:45 | 2011-04-22 | 75 | 1.25 | 0.052083 | 7395 | 123.25 | 5.1354 | 75 | 1.25 | 0.052083 | 4710 | 78.5 | 3.2708 | stuck
Wash and ream hole from ~920 mbsf. Circulate 100 bbl hi-vis mud sweep | 7:45 | 2011-04-22 | 10:00 | 2011-04-22 | 135 | 2.25 | 0.09375 | 7530 | 125.5 | 5.2292 | 135 | 2.25 | 0.09375 | 4845 | 80.75 | 3.3646
Work stuck pipe | 10:00 | 2011-04-22 | 12:00 | 2011-04-22 | 120 | 2 | 0.083333 | 7650 | 127.5 | 5.3125 | 120 | 2 | 0.083333 | 4965 | 82.75 | 3.4479 | stuck
Wash and ream hole from ~923 mbsf. Unable to pass bridge | 12:00 | 2011-04-22 | 21:00 | 2011-04-22 | 540 | 9 | 0.375 | 8190 | 136.5 | 5.6875 | 540 | 9 | 0.375 | 5505 | 91.75 | 3.8229
Pull back in the hole from 923 to 863.3 mbsf | 21:00 | 2011-04-22 | 21:30 | 2011-04-22 | 30 | 0.5 | 0.020833 | 8220 | 137 | 5.7083 | 30 | 0.5 | 0.020833 | 5535 | 92.25 | 3.8438
Rack top drive | 21:30 | 2011-04-22 | 22:00 | 2011-04-22 | 30 | 0.5 | 0.020833 | 8250 | 137.5 | 5.7292 | 30 | 0.5 | 0.020833 | 5565 | 92.75 | 3.8646
POOH with the drillstring and clear sea floor at 0005 hr and the plane of the rotary table at 0605 hr | 22:00 | 2011-04-22 | 6:00 | 2011-04-23 | 480 | 8 | 0.33333 | 8730 | 145.5 | 6.0625 | 480 | 8 | 0.33333 | 6045 | 100.75 | 4.1979 | Clear seafloor at 05:00. End Run 2 at 06:05.
Lay out junk baskets and 9 7/8” bit. Examination of the contents of the junk baskets was inconclusive but did yield some basaltic cuttings ranging from small gravel to rounded pebbles. The Exp 312 logs indicate a large washed out zone at ~920-935 mbsf which we will attempt to stabilize with a 5 bbl cement plug. | 6:00 | 2011-04-23 | 7:00 | 2011-04-23 | 60 | 1 | 0.041667 | 8790 | 146.5 | 6.1042 | 60 | 1 | 0.041667 | 6105 | 101.75 | 4.2396 | Samples Run02-EXJB. Decision to cement
Make up cementing BHA with used Reed tricone bit without jets and two stands of drill collars. Deploy to 2676 mbrf | 7:00 | 2011-04-23 | 13:00 | 2011-04-23 | 360 | 6 | 0.25 | 9150 | 152.5 | 6.3542 | 360 | 6 | 0.25 | 6465 | 107.75 | 4.4896 | Start Run 3. Reed tricone without jets
Install VIT | 13:00 | 2011-04-23 | 13:30 | 2011-04-23 | 30 | 0.5 | 0.020833 | 9180 | 153 | 6.375 | 30 | 0.5 | 0.020833 | 6495 | 108.25 | 4.5104
Resume RIH from 2676 to 3638 mbrf | 13:30 | 2011-04-23 | 15:00 | 2011-04-23 | 90 | 1.5 | 0.0625 | 9270 | 154.5 | 6.4375 | 90 | 1.5 | 0.0625 | 6585 | 109.75 | 4.5729
Search and position vessel. Reenter Hole 1256D at 1520 hr | 15:00 | 2011-04-23 | 15:15 | 2011-04-23 | 15 | 0.25 | 0.010417 | 9285 | 154.75 | 6.4479 | 15 | 0.25 | 0.010417 | 6600 | 110 | 4.5833 | Reentry 3
RIH with the drillstring to 262.9 mbsf | 15:15 | 2011-04-23 | 15:45 | 2011-04-23 | 30 | 0.5 | 0.020833 | 9315 | 155.25 | 6.4687 | 30 | 0.5 | 0.020833 | 6630 | 110.5 | 4.6042
POOH with VIT and recover same | 15:45 | 2011-04-23 | 17:15 | 2011-04-23 | 90 | 1.5 | 0.0625 | 9405 | 156.75 | 6.5312 | 90 | 1.5 | 0.0625 | 6720 | 112 | 4.6667
Resume RIH with the drillstring. Tag bridge at 922 mbsf | 17:15 | 2011-04-23 | 18:45 | 2011-04-23 | 90 | 1.5 | 0.0625 | 9495 | 158.25 | 6.5937 | 90 | 1.5 | 0.0625 | 6810 | 113.5 | 4.7292
Make up circulating head, Lo-torque valves, and pressure test to 1500 psi | 18:45 | 2011-04-23 | 19:15 | 2011-04-23 | 30 | 0.5 | 0.020833 | 9525 | 158.75 | 6.6146 | 30 | 0.5 | 0.020833 | 6840 | 114 | 4.75
Pump 5 bbls of 16 ppg cement slurry | 19:15 | 2011-04-23 | 19:30 | 2011-04-23 | 15 | 0.25 | 0.010417 | 9540 | 159 | 6.625 | 15 | 0.25 | 0.010417 | 6855 | 114.25 | 4.7604 | Pump cement
Displace drillstring with sea water (1 X volume) | 19:30 | 2011-04-23 | 20:00 | 2011-04-23 | 30 | 0.5 | 0.020833 | 9570 | 159.5 | 6.6458 | 30 | 0.5 | 0.020833 | 6885 | 114.75 | 4.7812
Lay out circulating head and pull back in the hole with the drillstring to 806.9 mbsf | 20:00 | 2011-04-23 | 20:30 | 2011-04-23 | 30 | 0.5 | 0.020833 | 9600 | 160 | 6.6667 | 30 | 0.5 | 0.020833 | 6915 | 115.25 | 4.8021
Flush drillstring with sea water (3 X volume) | 20:30 | 2011-04-23 | 21:45 | 2011-04-23 | 75 | 1.25 | 0.052083 | 9675 | 161.25 | 6.7187 | 75 | 1.25 | 0.052083 | 6990 | 116.5 | 4.8542
Lay out circulating head and POOH to 3191 mbrf. Clear top of the cone at 2320 hr. Bit at rotary table at 0515 hr | 21:45 | 2011-04-23 | 5:15 | 2011-04-24 | 450 | 7.5 | 0.3125 | 10125 | 168.75 | 7.0312 | 450 | 7.5 | 0.3125 | 7440 | 124 | 5.1667 | Clear seafloor at 23:20. End Run 3 at 05:15.
Make up new 9 7/8” Atlas tricone bit, inspect float, pick up two drill collar stands from derrick, and install piccolo at 199 mbrf | 5:15 | 2011-04-24 | 6:45 | 2011-04-24 | 90 | 1.5 | 0.0625 | 10215 | 170.25 | 7.0937 | 90 | 1.5 | 0.0625 | 7530 | 125.5 | 5.2292 | Start Run 4. 9 7/8” tricone bit (Atlas HP61)
Service rig | 6:45 | 2011-04-24 | 7:15 | 2011-04-24 | 30 | 0.5 | 0.020833 | 10245 | 170.75 | 7.1146 | 30 | 0.5 | 0.020833 | 7560 | 126 | 5.25
Resume tripping drillstring from 199 to 1596 mbrf | 7:15 | 2011-04-24 | 10:30 | 2011-04-24 | 195 | 3.25 | 0.13542 | 10440 | 174 | 7.25 | 195 | 3.25 | 0.13542 | 7755 | 129.25 | 5.3854
Slip and cut 115 feet of drilling line | 10:30 | 2011-04-24 | 12:00 | 2011-04-24 | 90 | 1.5 | 0.0625 | 10530 | 175.5 | 7.3125 | 90 | 1.5 | 0.0625 | 7845 | 130.75 | 5.4479
Resume tripping drillstring from 1596 to 2731 mbrf | 12:00 | 2011-04-24 | 14:30 | 2011-04-24 | 150 | 2.5 | 0.10417 | 10680 | 178 | 7.4167 | 150 | 2.5 | 0.10417 | 7995 | 133.25 | 5.5521
Deploy VIT | 14:30 | 2011-04-24 | 15:00 | 2011-04-24 | 30 | 0.5 | 0.020833 | 10710 | 178.5 | 7.4375 | 30 | 0.5 | 0.020833 | 8025 | 133.75 | 5.5729
Continue to RIH with the drillpipe from 2731 to 3636 mbrf | 15:00 | 2011-04-24 | 16:45 | 2011-04-24 | 105 | 1.75 | 0.072917 | 10815 | 180.25 | 7.5104 | 105 | 1.75 | 0.072917 | 8130 | 135.5 | 5.6458
Search and position vessel. Reenter Hole 1256D at 1655 hr | 16:45 | 2011-04-24 | 17:00 | 2011-04-24 | 15 | 0.25 | 0.010417 | 10830 | 180.5 | 7.5208 | 15 | 0.25 | 0.010417 | 8145 | 135.75 | 5.6562 | Reentry 4
Continue to RIH with the drillstring to 315.7 mbsf | 17:00 | 2011-04-24 | 17:30 | 2011-04-24 | 30 | 0.5 | 0.020833 | 10860 | 181 | 7.5417 | 30 | 0.5 | 0.020833 | 8175 | 136.25 | 5.6771
Recover VIT | 17:30 | 2011-04-24 | 18:15 | 2011-04-24 | 45 | 0.75 | 0.03125 | 10905 | 181.75 | 7.5729 | 45 | 0.75 | 0.03125 | 8220 | 137 | 5.7083
Continue to RIH with drillpipe and tag bridge at 922 mbsf | 18:15 | 2011-04-24 | 19:30 | 2011-04-24 | 75 | 1.25 | 0.052083 | 10980 | 183 | 7.625 | 75 | 1.25 | 0.052083 | 8295 | 138.25 | 5.7604
Pull back in the hole to 890.6 mbsf | 19:30 | 2011-04-24 | 19:45 | 2011-04-24 | 15 | 0.25 | 0.010417 | 10995 | 183.25 | 7.6354 | 15 | 0.25 | 0.010417 | 8310 | 138.5 | 5.7708
Pick up top drive and RIH with same to 922.0 mbsf | 19:45 | 2011-04-24 | 20:45 | 2011-04-24 | 60 | 1 | 0.041667 | 11055 | 184.25 | 7.6771 | 60 | 1 | 0.041667 | 8370 | 139.5 | 5.8125
Attempt to wash and ream though bridge encountering high erratic torque with TD max current = 650 amps | 20:45 | 2011-04-24 | 21:45 | 2011-04-24 | 60 | 1 | 0.041667 | 11115 | 185.25 | 7.7187 | 60 | 1 | 0.041667 | 8430 | 140.5 | 5.8542
Pull back in the hole with the top drive to 890.6 mbsf | 21:45 | 2011-04-24 | 22:15 | 2011-04-24 | 30 | 0.5 | 0.020833 | 11145 | 185.75 | 7.7396 | 30 | 0.5 | 0.020833 | 8460 | 141 | 5.875 | Decision to pump more cement
Rack top drive | 22:15 | 2011-04-24 | 22:45 | 2011-04-24 | 30 | 0.5 | 0.020833 | 11175 | 186.25 | 7.7604 | 30 | 0.5 | 0.020833 | 8490 | 141.5 | 5.8958
POOH with the drillstring from 890.6 to the surface. Clear sea floor at 0030 hr. Bit at rotary table at 0615 hr | 22:45 | 2011-04-24 | 6:15 | 2011-04-25 | 450 | 7.5 | 0.3125 | 11625 | 193.75 | 8.0729 | 450 | 7.5 | 0.3125 | 8940 | 149 | 6.2083 | Clear seafloor at 03:00. End Run 4 at 06:15.
Make up cementing bit (Reed type 517) without nozzles to 2 stands of drill collars and RIH to 2661 mbrf | 6:15 | 2011-04-25 | 12:15 | 2011-04-25 | 360 | 6 | 0.25 | 11985 | 199.75 | 8.3229 | 360 | 6 | 0.25 | 9300 | 155 | 6.4583 | Start Run 5. Cementing Bit (Reed type 517)
Deploy VIT | 12:15 | 2011-04-25 | 12:45 | 2011-04-25 | 30 | 0.5 | 0.020833 | 12015 | 200.25 | 8.3437 | 30 | 0.5 | 0.020833 | 9330 | 155.5 | 6.4792
Resume RIH with the drillstring from 2661 to 3637.8 mbrf | 12:45 | 2011-04-25 | 14:15 | 2011-04-25 | 90 | 1.5 | 0.0625 | 12105 | 201.75 | 8.4062 | 90 | 1.5 | 0.0625 | 9420 | 157 | 6.5417
Search and position vessel. Reenter Hole 1256D (#5) at 1445 hr | 14:15 | 2011-04-25 | 14:45 | 2011-04-25 | 30 | 0.5 | 0.020833 | 12135 | 202.25 | 8.4271 | 30 | 0.5 | 0.020833 | 9450 | 157.5 | 6.5625 | Reentry 5
Continue to RIH with the drillstring to 922 mbsf | 14:45 | 2011-04-25 | 17:15 | 2011-04-25 | 150 | 2.5 | 0.10417 | 12285 | 204.75 | 8.5312 | 150 | 2.5 | 0.10417 | 9600 | 160 | 6.6667
Install circulating head. Pressure test cement system | 17:15 | 2011-04-25 | 18:00 | 2011-04-25 | 45 | 0.75 | 0.03125 | 12330 | 205.5 | 8.5625 | 45 | 0.75 | 0.03125 | 9645 | 160.75 | 6.6979
Mix and pump 50 bbls of 15 ppg cement slurry | 18:00 | 2011-04-25 | 18:45 | 2011-04-25 | 45 | 0.75 | 0.03125 | 12375 | 206.25 | 8.5937 | 45 | 0.75 | 0.03125 | 9690 | 161.5 | 6.7292 | Pump cement
Displace cement slurry with sea water | 18:45 | 2011-04-25 | 19:00 | 2011-04-25 | 15 | 0.25 | 0.010417 | 12390 | 206.5 | 8.6042 | 15 | 0.25 | 0.010417 | 9705 | 161.75 | 6.7396
Lay out circulating head and pull back in the hole to 720.5 mbsf | 19:00 | 2011-04-25 | 19:45 | 2011-04-25 | 45 | 0.75 | 0.03125 | 12435 | 207.25 | 8.6354 | 45 | 0.75 | 0.03125 | 9750 | 162.5 | 6.7708
Circulate and flush drillpipe with 3X drillstring volume of sea water | 19:45 | 2011-04-25 | 20:45 | 2011-04-25 | 60 | 1 | 0.041667 | 12495 | 208.25 | 8.6771 | 60 | 1 | 0.041667 | 9810 | 163.5 | 6.8125
POOH with the drillstring to surface. Clear the top of the cone at 2215 hr. Bit at rotary table at 0345 hr | 20:45 | 2011-04-25 | 3:45 | 2011-04-26 | 420 | 7 | 0.29167 | 12915 | 215.25 | 8.9687 | 420 | 7 | 0.29167 | 10230 | 170.5 | 7.1042 | Clear seafloor at 22:15. End Run 5 at 03:45.
Lay down Reed bit and pick up 9 7/8” Atlas HP61 tricone with tandem set of boot baskets and two stands of drill collars. RIH to 200.6 mbrf | 3:45 | 2011-04-26 | 5:30 | 2011-04-26 | 105 | 1.75 | 0.072917 | 13020 | 217 | 9.0417 | 105 | 1.75 | 0.072917 | 10335 | 172.25 | 7.1771 | Start Run 6. 9 7/8” Atlas HP61 tricone + Boot Baskets
Service rig: drawworks, crown, pipe stabber, travelling block, and dollies | 5:30 | 2011-04-26 | 6:00 | 2011-04-26 | 30 | 0.5 | 0.020833 | 13050 | 217.5 | 9.0625 | 30 | 0.5 | 0.020833 | 10365 | 172.75 | 7.1979
Resume RIH from 2676 to 3533 mbrf | 6:00 | 2011-04-26 | 13:30 | 2011-04-26 | 450 | 7.5 | 0.3125 | 13500 | 225 | 9.375 | 450 | 7.5 | 0.3125 | 10815 | 180.25 | 7.5104
Deploy VIT | 13:30 | 2011-04-26 | 14:00 | 2011-04-26 | 30 | 0.5 | 0.020833 | 13530 | 225.5 | 9.3958 | 30 | 0.5 | 0.020833 | 10845 | 180.75 | 7.5312
RIH with the drillstring from 3533 to 3638 mbrf | 14:00 | 2011-04-26 | 15:00 | 2011-04-26 | 60 | 1 | 0.041667 | 13590 | 226.5 | 9.4375 | 60 | 1 | 0.041667 | 10905 | 181.75 | 7.5729
Search and position vessel. Reenter Hole 1256D (#6) at 1520 hr | 15:00 | 2011-04-26 | 15:15 | 2011-04-26 | 15 | 0.25 | 0.010417 | 13605 | 226.75 | 9.4479 | 15 | 0.25 | 0.010417 | 10920 | 182 | 7.5833 | Reentry 6
Resume RIH with the drillstring to 661.8 mbsf | 15:15 | 2011-04-26 | 17:00 | 2011-04-26 | 105 | 1.75 | 0.072917 | 13710 | 228.5 | 9.5208 | 105 | 1.75 | 0.072917 | 11025 | 183.75 | 7.6562
Recover VIT | 17:00 | 2011-04-26 | 17:30 | 2011-04-26 | 30 | 0.5 | 0.020833 | 13740 | 229 | 9.5417 | 30 | 0.5 | 0.020833 | 11055 | 184.25 | 7.6771
RIH with the drillstring and make firm contact with cement at 882.0 mbsf | 17:30 | 2011-04-26 | 18:15 | 2011-04-26 | 45 | 0.75 | 0.03125 | 13785 | 229.75 | 9.5729 | 45 | 0.75 | 0.03125 | 11100 | 185 | 7.7083
Pick up top drive | 18:15 | 2011-04-26 | 18:45 | 2011-04-26 | 30 | 0.5 | 0.020833 | 13815 | 230.25 | 9.5937 | 30 | 0.5 | 0.020833 | 11130 | 185.5 | 7.7292
Drill out cement from 882.0 to 922.0 mbsf. Circulate 40 bbl gel sweep at 904.6 mbsf | 18:45 | 2011-04-26 | 22:30 | 2011-04-26 | 225 | 3.75 | 0.15625 | 14040 | 234 | 9.75 | 225 | 3.75 | 0.15625 | 11355 | 189.25 | 7.8854
Attempt to drill through bridge with high erratic torque. Circulate 50 bbl gel sweep at 922 mbsf. Continue to wash and ream at 922.0 mbsf. Maximum TD current = 650 amps. | 22:30 | 2011-04-26 | 1:30 | 2011-04-27 | 180 | 3 | 0.125 | 14220 | 237 | 9.875 | 180 | 3 | 0.125 | 11535 | 192.25 | 8.0104
Work stuck pipe at ~923 mbsf. Maximum TD current = 800 amp with 120 Kips of overpull | 1:30 | 2011-04-27 | 2:30 | 2011-04-27 | 60 | 1 | 0.041667 | 14280 | 238 | 9.9167 | 60 | 1 | 0.041667 | 11595 | 193.25 | 8.0521
Resume washing and reaming ledge at 922 with high rotary speed, high pump, and lighter weight on bit. We appeared to be making progress mid morning only to lose it later in the day which may indicate that the obstruction is shifting. Circulate multiple 50 bbl hivis gel sweeps at 922 mbsf. Continue to wash and ream obstruction at 921.6 mbsf (tide +/- 0.5 m). Circulate 100 bbl hi-vis gel sweep at 922.0 mbsf. | 2:30 | 2011-04-27 | 6:00 | 2011-04-28 | 1650 | 27.5 | 1.1458 | 15930 | 265.5 | 11.0625 | 1650 | 27.5 | 1.1458 | 13245 | 220.75 | 9.1979
Pull back with the top drive from 921.6 to 834.5 mbsf | 6:00 | 2011-04-28 | 6:45 | 2011-04-28 | 45 | 0.75 | 0.03125 | 15975 | 266.25 | 11.0937 | 45 | 0.75 | 0.03125 | 13290 | 221.5 | 9.2292
Rack top drive | 6:45 | 2011-04-28 | 7:15 | 2011-04-28 | 30 | 0.5 | 0.020833 | 16005 | 266.75 | 11.1146 | 30 | 0.5 | 0.020833 | 13320 | 222 | 9.25
POOH from 834.5 mbsf and clear sea floor at 0850 hr. Set back drill collar stands in the derrick, and layout junk baskets. Bit is at the rotary table at 1455 hr. Lay out used bit in good condition with no appreciable shirt-tail wear, with all teeth intact, and exhibiting very little wear | 7:15 | 2011-04-28 | 15:00 | 2011-04-28 | 465 | 7.75 | 0.32292 | 16470 | 274.5 | 11.4375 | 465 | 7.75 | 0.32292 | 13785 | 229.75 | 9.5729 | Clear seafloor at at 08:50. End Run 6 at 14:55. Samples Run06-EXJB.
Make up new Smith tricone bit, bit sub with float, and four stands of drill collars and RIH with the drillstring to 2759 mbrf | 15:00 | 2011-04-28 | 20:45 | 2011-04-28 | 345 | 5.75 | 0.23958 | 16815 | 280.25 | 11.6771 | 345 | 5.75 | 0.23958 | 14130 | 235.5 | 9.8125 | Start Run 7 . Smith tricone bit.
Slip and cut 115 feet of drilling line | 20:45 | 2011-04-28 | 22:15 | 2011-04-28 | 90 | 1.5 | 0.0625 | 16905 | 281.75 | 11.7396 | 90 | 1.5 | 0.0625 | 14220 | 237 | 9.875
install VIT | 22:15 | 2011-04-28 | 22:45 | 2011-04-28 | 30 | 0.5 | 0.020833 | 16935 | 282.25 | 11.7604 | 30 | 0.5 | 0.020833 | 14250 | 237.5 | 9.8958
Resume RIH with the drillstring from 2759 to 3640 mbrf. Fill drillpipe every 10 stands | 22:45 | 2011-04-28 | 0:45 | 2011-04-29 | 120 | 2 | 0.083333 | 17055 | 284.25 | 11.8437 | 120 | 2 | 0.083333 | 14370 | 239.5 | 9.9792
Space out and position vessel to reenter Hole 1256D at 0135 hr (#7) | 0:45 | 2011-04-29 | 1:30 | 2011-04-29 | 45 | 0.75 | 0.03125 | 17100 | 285 | 11.875 | 45 | 0.75 | 0.03125 | 14415 | 240.25 | 10.0104 | Reentry 7
RIH to 228.2 mbsf | 1:30 | 2011-04-29 | 3:00 | 2011-04-29 | 90 | 1.5 | 0.0625 | 17190 | 286.5 | 11.9375 | 90 | 1.5 | 0.0625 | 14505 | 241.75 | 10.0729
Retrieve and recover VIT | 3:00 | 2011-04-29 | 3:30 | 2011-04-29 | 30 | 0.5 | 0.020833 | 17220 | 287 | 11.9583 | 30 | 0.5 | 0.020833 | 14535 | 242.25 | 10.0938
Resume RIH from 228.2 to 861.4 mbsf | 3:30 | 2011-04-29 | 4:45 | 2011-04-29 | 75 | 1.25 | 0.052083 | 17295 | 288.25 | 12.0104 | 75 | 1.25 | 0.052083 | 14610 | 243.5 | 10.1458
Pick up top drive | 4:45 | 2011-04-29 | 5:15 | 2011-04-29 | 30 | 0.5 | 0.020833 | 17325 | 288.75 | 12.0312 | 30 | 0.5 | 0.020833 | 14640 | 244 | 10.1667
RIH with the top drive from 861.4 to 921.9 mbsf | 5:15 | 2011-04-29 | 6:15 | 2011-04-29 | 60 | 1 | 0.041667 | 17385 | 289.75 | 12.0729 | 60 | 1 | 0.041667 | 14700 | 245 | 10.2083
Attempt to pass obstruction with pump and no rotation. No advance. | 6:15 | 2011-04-29 | 7:00 | 2011-04-29 | 45 | 0.75 | 0.03125 | 17430 | 290.5 | 12.1042 | 45 | 0.75 | 0.03125 | 14745 | 245.75 | 10.2396
Resume washing and reaming, drill through obstruction at 935.0 mbsf, and advance from 921.9 to 941.5 mbsf. Circulate 100 bbl gel sweep at 931.0 mbsf. | 7:00 | 2011-04-29 | 0:00 | 2011-04-30 | 1020 | 17 | 0.70833 | 18450 | 307.5 | 12.8125 | 1020 | 17 | 0.70833 | 15765 | 262.75 | 10.9479 | Finally!
Continue to wash and ream from 941.5 to 1143.2 mbsf. High torque and pump pressure increase of 500 psi when picking off slips at last connection. Circulate 50 bbls hi-vis gel sweeps at 988.6 and 1113.6 mbsf | 0:00 | 2011-04-30 | 12:30 | 2011-04-30 | 750 | 12.5 | 0.52083 | 19200 | 320 | 13.3333 | 750 | 12.5 | 0.52083 | 16515 | 275.25 | 11.4688
Work back to 1114.4 mbsf and work out excess pump pressure and torque | 12:30 | 2011-04-30 | 14:00 | 2011-04-30 | 90 | 1.5 | 0.0625 | 19290 | 321.5 | 13.3958 | 90 | 1.5 | 0.0625 | 16605 | 276.75 | 11.5313
Resume washing and reaming from 1143.2 to 1162.4 mbsf. High torque and increase of 500 psi pump pressure when coming off slips on last connection. | 14:00 | 2011-04-30 | 16:30 | 2011-04-30 | 150 | 2.5 | 0.10417 | 19440 | 324 | 13.5 | 150 | 2.5 | 0.10417 | 16755 | 279.25 | 11.6354
Work stuck pipe free | 16:30 | 2011-04-30 | 18:30 | 2011-04-30 | 120 | 2 | 0.083333 | 19560 | 326 | 13.5833 | 120 | 2 | 0.083333 | 16875 | 281.25 | 11.7188
Wash and ream from 1162.4 to 1507.1 mbsf. Circulate 50 bbls hi-vis gel sweeps at 1142.6 and 1253.6 mbsf. Find 6 m of hard fill. | 18:30 | 2011-04-30 | 9:15 | 2011-05-01 | 885 | 14.75 | 0.61458 | 20445 | 340.75 | 14.1979 | 885 | 14.75 | 0.61458 | 17760 | 296 | 12.3333 | bottom of the hole
Circulate 100 bbls hi-vis gel sweep | 9:15 | 2011-05-01 | 10:30 | 2011-05-01 | 75 | 1.25 | 0.052083 | 20520 | 342 | 14.25 | 75 | 1.25 | 0.052083 | 17835 | 297.25 | 12.3854
Pull back in the hole from 1507.1 to 1265.0 mbsf | 10:30 | 2011-05-01 | 12:15 | 2011-05-01 | 105 | 1.75 | 0.072917 | 20625 | 343.75 | 14.3229 | 105 | 1.75 | 0.072917 | 17940 | 299 | 12.4583
Set back top drive | 12:15 | 2011-05-01 | 12:45 | 2011-05-01 | 30 | 0.5 | 0.020833 | 20655 | 344.25 | 14.3438 | 30 | 0.5 | 0.020833 | 17970 | 299.5 | 12.4792
Pull back in the hole with the drillstring from 1265.0 to 890.5 mbsf | 12:45 | 2011-05-01 | 14:45 | 2011-05-01 | 120 | 2 | 0.083333 | 20775 | 346.25 | 14.4271 | 120 | 2 | 0.083333 | 18090 | 301.5 | 12.5625
Pick up top drive | 14:45 | 2011-05-01 | 15:30 | 2011-05-01 | 45 | 0.75 | 0.03125 | 20820 | 347 | 14.4583 | 45 | 0.75 | 0.03125 | 18135 | 302.25 | 12.5938
RIH with the drillstring and top drive to 967.3 mbsf with no drag or overpull | 15:30 | 2011-05-01 | 16:30 | 2011-05-01 | 60 | 1 | 0.041667 | 20880 | 348 | 14.5 | 60 | 1 | 0.041667 | 18195 | 303.25 | 12.6354
Break circulation and spot 60 bbl of 10.5 ppg mud at 967 mbsf | 16:30 | 2011-05-01 | 17:00 | 2011-05-01 | 30 | 0.5 | 0.020833 | 20910 | 348.5 | 14.5208 | 30 | 0.5 | 0.020833 | 18225 | 303.75 | 12.6563
Pull back in the hole with the top drive to 861.7 mbsf | 17:00 | 2011-05-01 | 17:45 | 2011-05-01 | 45 | 0.75 | 0.03125 | 20955 | 349.25 | 14.5521 | 45 | 0.75 | 0.03125 | 18270 | 304.5 | 12.6875
Rack top drive | 17:45 | 2011-05-01 | 18:15 | 2011-05-01 | 30 | 0.5 | 0.020833 | 20985 | 349.75 | 14.5729 | 30 | 0.5 | 0.020833 | 18300 | 305 | 12.7083
Pull out of the hole with the top drive. Clear the top of the cone at 20:05 hr. Continue to POOH. Bit at rotary table at 0245 hr. | 18:15 | 2011-05-01 | 2:45 | 2011-05-02 | 510 | 8.5 | 0.35417 | 21495 | 358.25 | 14.9271 | 510 | 8.5 | 0.35417 | 18810 | 313.5 | 13.0625 | Clear seafloor at 20:05. End Run 7 at 02:45.
Make up cement BHA with used Reed 9 7/8” bit (without jets) and RIH to 144 mbrf | 2:45 | 2011-05-02 | 3:30 | 2011-05-02 | 45 | 0.75 | 0.03125 | 21540 | 359 | 14.9583 | 45 | 0.75 | 0.03125 | 18855 | 314.25 | 13.0938 | Start Run 8. Cementing bit (used Reed 9 7/8")
Service rig | 3:30 | 2011-05-02 | 4:00 | 2011-05-02 | 30 | 0.5 | 0.020833 | 21570 | 359.5 | 14.9792 | 30 | 0.5 | 0.020833 | 18885 | 314.75 | 13.1146
RIH from 144 to 2676 mbrf. Fill drillpipe every 10 stands | 4:00 | 2011-05-02 | 9:00 | 2011-05-02 | 300 | 5 | 0.20833 | 21870 | 364.5 | 15.1875 | 300 | 5 | 0.20833 | 19185 | 319.75 | 13.3229
Launch VIT | 9:00 | 2011-05-02 | 9:45 | 2011-05-02 | 45 | 0.75 | 0.03125 | 21915 | 365.25 | 15.2188 | 45 | 0.75 | 0.03125 | 19230 | 320.5 | 13.3542
Resume RIH from 2676 to 3637 mbrf | 9:45 | 2011-05-02 | 12:45 | 2011-05-02 | 180 | 3 | 0.125 | 22095 | 368.25 | 15.3438 | 180 | 3 | 0.125 | 19410 | 323.5 | 13.4792
Search and position vessel. Reenter Hole 1256D at 1300 hr. | 12:45 | 2011-05-02 | 13:00 | 2011-05-02 | 15 | 0.25 | 0.010417 | 22110 | 368.5 | 15.3542 | 15 | 0.25 | 0.010417 | 19425 | 323.75 | 13.4896 | Reentry 8
Resume RIH to 490.3 mbsf | 13:00 | 2011-05-02 | 14:15 | 2011-05-02 | 75 | 1.25 | 0.052083 | 22185 | 369.75 | 15.4063 | 75 | 1.25 | 0.052083 | 19500 | 325 | 13.5417
Recover VIT | 14:15 | 2011-05-02 | 14:45 | 2011-05-02 | 30 | 0.5 | 0.020833 | 22215 | 370.25 | 15.4271 | 30 | 0.5 | 0.020833 | 19530 | 325.5 | 13.5625
Continue to RIH with drillpipe to 960.5 mbsf | 14:45 | 2011-05-02 | 16:15 | 2011-05-02 | 90 | 1.5 | 0.0625 | 22305 | 371.75 | 15.4896 | 90 | 1.5 | 0.0625 | 19620 | 327 | 13.625
Make up circulating head and pressure test same to 2000 psi | 16:15 | 2011-05-02 | 16:45 | 2011-05-02 | 30 | 0.5 | 0.020833 | 22335 | 372.25 | 15.5104 | 30 | 0.5 | 0.020833 | 19650 | 327.5 | 13.6458
Mix and pump 60 barrels of 15 ppg cement slurry | 16:45 | 2011-05-02 | 17:15 | 2011-05-02 | 30 | 0.5 | 0.020833 | 22365 | 372.75 | 15.5313 | 30 | 0.5 | 0.020833 | 19680 | 328 | 13.6667
Displace cement with sea water | 17:15 | 2011-05-02 | 17:45 | 2011-05-02 | 30 | 0.5 | 0.020833 | 22395 | 373.25 | 15.5521 | 30 | 0.5 | 0.020833 | 19710 | 328.5 | 13.6875
Lay out circulating head and pull back in the hole to 605.5 mbsf | 17:45 | 2011-05-02 | 18:45 | 2011-05-02 | 60 | 1 | 0.041667 | 22455 | 374.25 | 15.5938 | 60 | 1 | 0.041667 | 19770 | 329.5 | 13.7292
Flush drillstring with 3 drillpipe volumes of seawater | 18:45 | 2011-05-02 | 19:45 | 2011-05-02 | 60 | 1 | 0.041667 | 22515 | 375.25 | 15.6354 | 60 | 1 | 0.041667 | 19830 | 330.5 | 13.7708
POOH with the drillstring. Clear seafloor at 2105 hr. Bit at rotary table at 0315 hr. | 19:45 | 2011-05-02 | 3:15 | 2011-05-03 | 450 | 7.5 | 0.3125 | 22965 | 382.75 | 15.9479 | 450 | 7.5 | 0.3125 | 20280 | 338 | 14.0833 | Clear seafloor at 03:15. End Run 8 at 03:15
Lay out Reed tricone bit and pick up RCB assembly and RIH to 200 mbrf. Space out RCB assembly | 3:15 | 2011-05-03 | 6:00 | 2011-05-03 | 165 | 2.75 | 0.11458 | 23130 | 385.5 | 16.0625 | 165 | 2.75 | 0.11458 | 20445 | 340.75 | 14.1979 | Start Run 9. RCB assembly
Service rig and RIS load pin transmitters | 6:00 | 2011-05-03 | 6:30 | 2011-05-03 | 30 | 0.5 | 0.020833 | 23160 | 386 | 16.0833 | 30 | 0.5 | 0.020833 | 20475 | 341.25 | 14.2188
RIH with the drillpipe from 200 to 2732 mbrf | 6:30 | 2011-05-03 | 10:30 | 2011-05-03 | 240 | 4 | 0.16667 | 23400 | 390 | 16.25 | 240 | 4 | 0.16667 | 20715 | 345.25 | 14.3854
Deploy VIT | 10:30 | 2011-05-03 | 11:00 | 2011-05-03 | 30 | 0.5 | 0.020833 | 23430 | 390.5 | 16.2708 | 30 | 0.5 | 0.020833 | 20745 | 345.75 | 14.4063
Resume RIH from 2732 to 3637 mbrf | 11:00 | 2011-05-03 | 12:15 | 2011-05-03 | 75 | 1.25 | 0.052083 | 23505 | 391.75 | 16.3229 | 75 | 1.25 | 0.052083 | 20820 | 347 | 14.4583
Search and position for reentry. Reenter Hole 1256D (#8) at 1235 hr | 12:15 | 2011-05-03 | 12:30 | 2011-05-03 | 15 | 0.25 | 0.010417 | 23520 | 392 | 16.3333 | 15 | 0.25 | 0.010417 | 20835 | 347.25 | 14.4688 | Reentry 9
RIH with the drillpipe to 690.2 mbsf | 12:30 | 2011-05-03 | 13:45 | 2011-05-03 | 75 | 1.25 | 0.052083 | 23595 | 393.25 | 16.3854 | 75 | 1.25 | 0.052083 | 20910 | 348.5 | 14.5208
RIH with the drillpipe and tag contact (ledge or top of plug) at 924.0 mbsf | 13:45 | 2011-05-03 | 15:00 | 2011-05-03 | 75 | 1.25 | 0.052083 | 23670 | 394.5 | 16.4375 | 75 | 1.25 | 0.052083 | 20985 | 349.75 | 14.5729
Pull back in the hole from 924.0 to 891.5 mbsf | 15:00 | 2011-05-03 | 15:15 | 2011-05-03 | 15 | 0.25 | 0.010417 | 23685 | 394.75 | 16.4479 | 15 | 0.25 | 0.010417 | 21000 | 350 | 14.5833
Pick up top drive | 15:15 | 2011-05-03 | 16:00 | 2011-05-03 | 45 | 0.75 | 0.03125 | 23730 | 395.5 | 16.4792 | 45 | 0.75 | 0.03125 | 21045 | 350.75 | 14.6146
Drill non-mag core barrels and drop same. Establish slow circulating rate parameters. | 16:00 | 2011-05-03 | 17:45 | 2011-05-03 | 105 | 1.75 | 0.072917 | 23835 | 397.25 | 16.5521 | 105 | 1.75 | 0.072917 | 21150 | 352.5 | 14.6875
Cut cement cores 1256D-1G to -5G from 924.0 to 971.3 mbsf | 17:45 | 2011-05-03 | 6:00 | 2011-05-04 | 735 | 12.25 | 0.51042 | 24570 | 409.5 | 17.0625 | 735 | 12.25 | 0.51042 | 21885 | 364.75 | 15.1979
Pull back in the hole to 833.9 mbsf | 6:00 | 2011-05-04 | 6:45 | 2011-05-04 | 45 | 0.75 | 0.03125 | 24615 | 410.25 | 17.0938 | 45 | 0.75 | 0.03125 | 21930 | 365.5 | 15.2292
Rack top drive | 6:45 | 2011-05-04 | 7:15 | 2011-05-04 | 30 | 0.5 | 0.020833 | 24645 | 410.75 | 17.1146 | 30 | 0.5 | 0.020833 | 21960 | 366 | 15.25
Slip and cut 115 feet of drilling line | 7:15 | 2011-05-04 | 8:45 | 2011-05-04 | 90 | 1.5 | 0.0625 | 24735 | 412.25 | 17.1771 | 90 | 1.5 | 0.0625 | 22050 | 367.5 | 15.3125
Drop wash barrel | 8:45 | 2011-05-04 | 9:00 | 2011-05-04 | 15 | 0.25 | 0.010417 | 24750 | 412.5 | 17.1875 | 15 | 0.25 | 0.010417 | 22065 | 367.75 | 15.3229
RIH from 833.9 to 949.1 mbf | 9:00 | 2011-05-04 | 9:30 | 2011-05-04 | 30 | 0.5 | 0.020833 | 24780 | 413 | 17.2083 | 30 | 0.5 | 0.020833 | 22095 | 368.25 | 15.3438
Pick up top drive | 9:30 | 2011-05-04 | 10:00 | 2011-05-04 | 30 | 0.5 | 0.020833 | 24810 | 413.5 | 17.2292 | 30 | 0.5 | 0.020833 | 22125 | 368.75 | 15.3646
Continue to RIH with the top drive from 949.1 to 971.3 mbsf | 10:00 | 2011-05-04 | 10:30 | 2011-05-04 | 30 | 0.5 | 0.020833 | 24840 | 414 | 17.25 | 30 | 0.5 | 0.020833 | 22155 | 369.25 | 15.3854
Round trip wash barrel and core 1256D-6G 971.3 to 980.9 mbsf | 10:30 | 2011-05-04 | 13:30 | 2011-05-04 | 180 | 3 | 0.125 | 25020 | 417 | 17.375 | 180 | 3 | 0.125 | 22335 | 372.25 | 15.5104
Drop wash barrel and wash from 980.9 to 1507.1 mbsf. Note tight hole from 1499.6 to 1501.1 mbsf. Pump 50-bbl hi-sweeps at 1154.6 and 1501.1 mbsf | 13:30 | 2011-05-04 | 22:45 | 2011-05-04 | 555 | 9.25 | 0.38542 | 25575 | 426.25 | 17.7604 | 555 | 9.25 | 0.38542 | 22890 | 381.5 | 15.8958
Circulate 50-bbl hi-vis gel sweep | 22:45 | 2011-05-04 | 23:45 | 2011-05-04 | 60 | 1 | 0.041667 | 25635 | 427.25 | 17.8021 | 60 | 1 | 0.041667 | 22950 | 382.5 | 15.9375
Deploy sinker bars. Round trip wash barrel at 1497.0 mbsf. Drop fresh core barrel. | 23:45 | 2011-05-04 | 1:45 | 2011-05-05 | 120 | 2 | 0.083333 | 25755 | 429.25 | 17.8854 | 120 | 2 | 0.083333 | 23070 | 384.5 | 16.0208
RCB core 1256D-R235 to –R236 from 1507.1 to 1516.5 mbsf. Employing half-cores with no liners to improve recovery. All cores obtained with non-magnetic core barrels. | 1:45 | 2011-05-05 | 17:00 | 2011-05-05 | 915 | 15.25 | 0.63542 | 26670 | 444.5 | 18.5208 | 915 | 15.25 | 0.63542 | 23985 | 399.75 | 16.6563 | First 335 core! 235R (7%), 236R (13%)
Attempt to core –R237 from 1516.5 to 1518.2 mbsf with maximum overpull = 60 Kips, maximum TD current = 800 amps. WOB = 0. | 17:00 | 2011-05-05 | 20:30 | 2011-05-05 | 210 | 3.5 | 0.14583 | 26880 | 448 | 18.6667 | 210 | 3.5 | 0.14583 | 24195 | 403.25 | 16.8021
RIH with the coring line and retrieve 1256D-R237 (1516.5 to 1518.2 mbsf). Circulate 50 and 100 bbl hi-vis gel sweeps at 1518.2 mbsf. | 20:30 | 2011-05-05 | 21:45 | 2011-05-05 | 75 | 1.25 | 0.052083 | 26955 | 449.25 | 18.7188 | 75 | 1.25 | 0.052083 | 24270 | 404.5 | 16.8542 | 237R (empty)
Drop core barrel and attempt to core –R238 from 1518.2 mbsf to 1520.2 mbsf (tidal = +/- 0.8 m). Pump 50-bbl hi-vis sweep at 1520.2 mbsf. Average ROP for May 5 was 0.7 m/hr. | 21:45 | 2011-05-05 | 12:00 | 2011-05-06 | 855 | 14.25 | 0.59375 | 27810 | 463.5 | 19.3125 | 855 | 14.25 | 0.59375 | 25125 | 418.75 | 17.4479
RIH with the sinker bars and recover core barrel containing 20 cm roller | 12:00 | 2011-05-06 | 13:30 | 2011-05-06 | 90 | 1.5 | 0.0625 | 27900 | 465 | 19.375 | 90 | 1.5 | 0.0625 | 25215 | 420.25 | 17.5104 | 238R
Drop bit deplugger. Examine core catcher sub and found about 0.5” abraded away indicating downhole mechanical problem. | 13:30 | 2011-05-06 | 14:00 | 2011-05-06 | 30 | 0.5 | 0.020833 | 27930 | 465.5 | 19.3958 | 30 | 0.5 | 0.020833 | 25245 | 420.75 | 17.5313
RIH with the sinker bars and recover deplugger. Lay out same. Pump 70 bbls of 10.5 ppg mud. | 14:00 | 2011-05-06 | 15:15 | 2011-05-06 | 75 | 1.25 | 0.052083 | 28005 | 466.75 | 19.4479 | 75 | 1.25 | 0.052083 | 25320 | 422 | 17.5833
Rack top drive | 15:15 | 2011-05-06 | 16:45 | 2011-05-06 | 90 | 1.5 | 0.0625 | 28095 | 468.25 | 19.5104 | 90 | 1.5 | 0.0625 | 25410 | 423.5 | 17.6458
Pull back in the hole with the drillstring to 58.2 mbsf | 16:45 | 2011-05-06 | 20:30 | 2011-05-06 | 225 | 3.75 | 0.15625 | 28320 | 472 | 19.6667 | 225 | 3.75 | 0.15625 | 25635 | 427.25 | 17.8021
Flush drillstring with seawater to clean reentry cone of cuttings | 20:30 | 2011-05-06 | 21:00 | 2011-05-06 | 30 | 0.5 | 0.020833 | 28350 | 472.5 | 19.6875 | 30 | 0.5 | 0.020833 | 25665 | 427.75 | 17.8229
POOH with the drillpipe to the surface. Clear the seafloor at 2115 hr. Clear the rotary at 0545 hr. Bit body honed to a smooth profile at the bottom and on the sides. Bit missing all four cones, four legs, and core guides. Bit spiral stabilizer blades and embedded TCI inserts absent. Bit totally unrecognizable. | 21:00 | 2011-05-06 | 5:45 | 2011-05-07 | 525 | 8.75 | 0.36458 | 28875 | 481.25 | 20.0521 | 525 | 8.75 | 0.36458 | 26190 | 436.5 | 18.1875 | Clear seafloor at 21:15. End Run 9 at 05:45. Bit disintegrated
Prepare and make up Bowen 9” fishing magnet with 2 boot baskets to two stands of drill collars and RIH to 147 mbrf. | 5:45 | 2011-05-07 | 8:45 | 2011-05-07 | 180 | 3 | 0.125 | 29055 | 484.25 | 20.1771 | 180 | 3 | 0.125 | 26370 | 439.5 | 18.3125 | Start Run 10. Bowen 9" fishing magnet + 2 junk baskets
Service rig | 8:45 | 2011-05-07 | 9:15 | 2011-05-07 | 30 | 0.5 | 0.020833 | 29085 | 484.75 | 20.1979 | 30 | 0.5 | 0.020833 | 26400 | 440 | 18.3333
Resume RIH from 147 to 2680 mbrf | 9:15 | 2011-05-07 | 14:15 | 2011-05-07 | 300 | 5 | 0.20833 | 29385 | 489.75 | 20.4062 | 300 | 5 | 0.20833 | 26700 | 445 | 18.5417
Install VIT | 14:15 | 2011-05-07 | 14:45 | 2011-05-07 | 30 | 0.5 | 0.020833 | 29415 | 490.25 | 20.4271 | 30 | 0.5 | 0.020833 | 26730 | 445.5 | 18.5625
Resume RIH with the drillstring from 2680 to 3632 mbrf | 14:45 | 2011-05-07 | 16:30 | 2011-05-07 | 105 | 1.75 | 0.072917 | 29520 | 492 | 20.5 | 105 | 1.75 | 0.072917 | 26835 | 447.25 | 18.6354
Search and position vessel for reentry. Observe reentry cone clouded over with mud. Attempt reentry, miss cone, and pull back. Break circulation and reenter (#10) Hole 1256D at 1815 hr. | 16:30 | 2011-05-07 | 18:15 | 2011-05-07 | 105 | 1.75 | 0.072917 | 29625 | 493.75 | 20.5729 | 105 | 1.75 | 0.072917 | 26940 | 449 | 18.7083 | Reentry 10
RIH with the drillstring to 580.1 mbsf | 18:15 | 2011-05-07 | 19:30 | 2011-05-07 | 75 | 1.25 | 0.052083 | 29700 | 495 | 20.625 | 75 | 1.25 | 0.052083 | 27015 | 450.25 | 18.7604
Recover VIT | 19:30 | 2011-05-07 | 20:00 | 2011-05-07 | 30 | 0.5 | 0.020833 | 29730 | 495.5 | 20.6458 | 30 | 0.5 | 0.020833 | 27045 | 450.75 | 18.7812
RIH with the drillpipe from 580.1 to 1294.6 mbsf. Contact ledge that takes 10 Kips. | 20:00 | 2011-05-07 | 22:15 | 2011-05-07 | 135 | 2.25 | 0.09375 | 29865 | 497.75 | 20.7396 | 135 | 2.25 | 0.09375 | 27180 | 453 | 18.875
Pick up top drive | 22:15 | 2011-05-07 | 22:45 | 2011-05-07 | 30 | 0.5 | 0.020833 | 29895 | 498.25 | 20.7604 | 30 | 0.5 | 0.020833 | 27210 | 453.5 | 18.8958
RIH with the TD to 1328.7 mbsf to 1434.2 mbsf. Tight hole at 1328.7 mbsf which takes 10 Kips. Excessive rotary current at 20 SPM. Note increase in pump pressure (2500 psi at 20 SPM). Bleed off pressure at rig floor. | 22:45 | 2011-05-07 | 1:45 | 2011-05-08 | 180 | 3 | 0.125 | 30075 | 501.25 | 20.8854 | 180 | 3 | 0.125 | 27390 | 456.5 | 19.0208
Pull back in the hole from 1434.2 to 1395.8 mbsf and attempt to unplug drillstring with high pressure. No joy. | 1:45 | 2011-05-08 | 3:00 | 2011-05-08 | 75 | 1.25 | 0.052083 | 30150 | 502.5 | 20.9375 | 75 | 1.25 | 0.052083 | 27465 | 457.75 | 19.0729
Pull back in the hole from 1395.8 to 1242.3 mbsf with top drive | 3:00 | 2011-05-08 | 4:30 | 2011-05-08 | 90 | 1.5 | 0.0625 | 30240 | 504 | 21 | 90 | 1.5 | 0.0625 | 27555 | 459.25 | 19.1354
Rack top drive | 4:30 | 2011-05-08 | 5:00 | 2011-05-08 | 30 | 0.5 | 0.020833 | 30270 | 504.5 | 21.0208 | 30 | 0.5 | 0.020833 | 27585 | 459.75 | 19.1562
Pull back in the hole from 1242.3 to 264.2 mbsf to just inside casing shoe | 5:00 | 2011-05-08 | 7:00 | 2011-05-08 | 120 | 2 | 0.083333 | 30390 | 506.5 | 21.1042 | 120 | 2 | 0.083333 | 27705 | 461.75 | 19.2396
Attempt to circulate with circulating head. No Joy. | 7:00 | 2011-05-08 | 7:15 | 2011-05-08 | 15 | 0.25 | 0.010417 | 30405 | 506.75 | 21.1146 | 15 | 0.25 | 0.010417 | 27720 | 462 | 19.25
POOH from 264.2 mbsf and clear sea floor at 0755 hr. Recover drillstring and set back 2 stands of drill collars. Find 4 m of fine cuttings plugging inside of bit sub and the two junk baskets. Clean out same. Lay out magnet which is at the rotary at 1555 hr. | 7:15 | 2011-05-08 | 16:00 | 2011-05-08 | 525 | 8.75 | 0.36458 | 30930 | 515.5 | 21.4792 | 525 | 8.75 | 0.36458 | 28245 | 470.75 | 19.6146 | Clear seafloor at 07:55. End Run 10 at 15:55. Bit sub and junk basket filled with cuttings. Samples Run10-DC, Run10-EXJB, and Run10-FM
Make up Atlas tricone bit to dual set of junk baskets with 3 drill collar stands and deploy to 2704 mbrf. | 16:00 | 2011-05-08 | 0:00 | 2011-05-09 | 480 | 8 | 0.33333 | 31410 | 523.5 | 21.8125 | 480 | 8 | 0.33333 | 28725 | 478.75 | 19.9479 | Start Run 11. Atlas tricone bit + junk baskets
Launch VIT | 0:00 | 2011-05-09 | 1:00 | 2011-05-09 | 60 | 1 | 0.041667 | 31470 | 524.5 | 21.8542 | 60 | 1 | 0.041667 | 28785 | 479.75 | 19.9896
Continue to RIH with the drillpipe from 2704 to 3637 mbrf. Fill every 10 stands. | 1:00 | 2011-05-09 | 3:00 | 2011-05-09 | 120 | 2 | 0.083333 | 31590 | 526.5 | 21.9375 | 120 | 2 | 0.083333 | 28905 | 481.75 | 20.0729
Space out and reenter Hole 1256D at 0315 hr (#11) | 3:00 | 2011-05-09 | 3:15 | 2011-05-09 | 15 | 0.25 | 0.010417 | 31605 | 526.75 | 21.9479 | 15 | 0.25 | 0.010417 | 28920 | 482 | 20.0833 | Reentry 11
Continue to RIH to 461.2 mbsf | 3:15 | 2011-05-09 | 4:15 | 2011-05-09 | 60 | 1 | 0.041667 | 31665 | 527.75 | 21.9896 | 60 | 1 | 0.041667 | 28980 | 483 | 20.125
Recover VIT | 4:15 | 2011-05-09 | 4:45 | 2011-05-09 | 30 | 0.5 | 0.020833 | 31695 | 528.25 | 22.0104 | 30 | 0.5 | 0.020833 | 29010 | 483.5 | 20.1458
Resume RIH from 461.2 to 1356.1 mbsf where bit contacts ledge. Pull back to 1324.3mbsf | 4:45 | 2011-05-09 | 7:15 | 2011-05-09 | 150 | 2.5 | 0.10417 | 31845 | 530.75 | 22.1146 | 150 | 2.5 | 0.10417 | 29160 | 486 | 20.25
Pickup top drive and obtain slow circulating rate parameters | 7:15 | 2011-05-09 | 7:45 | 2011-05-09 | 30 | 0.5 | 0.020833 | 31875 | 531.25 | 22.1354 | 30 | 0.5 | 0.020833 | 29190 | 486.5 | 20.2708
Clean up ledge at 1356.1 mbsf and continue in the hole to 1442.5 mbsf. | 7:45 | 2011-05-09 | 9:15 | 2011-05-09 | 90 | 1.5 | 0.0625 | 31965 | 532.75 | 22.1979 | 90 | 1.5 | 0.0625 | 29280 | 488 | 20.3333
Circulate 100 bbl hi-vis gel sweep at 1442.5 mbsf | 9:15 | 2011-05-09 | 10:00 | 2011-05-09 | 45 | 0.75 | 0.03125 | 32010 | 533.5 | 22.2292 | 45 | 0.75 | 0.03125 | 29325 | 488.75 | 20.3646
RIH from 1442.5 to 1520.3 mbsf. Clean up under-gage areas of hole with maximum TD current = 500 amps | 10:00 | 2011-05-09 | 11:30 | 2011-05-09 | 90 | 1.5 | 0.0625 | 32100 | 535 | 22.2917 | 90 | 1.5 | 0.0625 | 29415 | 490.25 | 20.4271
Circulate 100 bbl hi-vis gel sweep at 1520.3 mbsf | 11:30 | 2011-05-09 | 12:00 | 2011-05-09 | 30 | 0.5 | 0.020833 | 32130 | 535.5 | 22.3125 | 30 | 0.5 | 0.020833 | 29445 | 490.75 | 20.4479
Continue to circulate hole clean and work rat-hole at 1520.3 mbsf. Circulate 100 bbl hi-vis gel sweep and circulate seawater (3 times volume of annulus) | 12:00 | 2011-05-09 | 16:15 | 2011-05-09 | 255 | 4.25 | 0.17708 | 32385 | 539.75 | 22.4896 | 255 | 4.25 | 0.17708 | 29700 | 495 | 20.625
Pull back in the hole with the top drive from 1520.3 to 1363.0 mbsf | 16:15 | 2011-05-09 | 17:45 | 2011-05-09 | 90 | 1.5 | 0.0625 | 32475 | 541.25 | 22.5521 | 90 | 1.5 | 0.0625 | 29790 | 496.5 | 20.6875
RIH with the top drive and tag ledge at 1473 mbsf. Work through ledge with pumps and rotation. Observe excess pump pressure and torque off slips at 1477.5 mbsf. Unable to pump. Reestablish rotation and circulation. | 17:45 | 2011-05-09 | 19:30 | 2011-05-09 | 105 | 1.75 | 0.072917 | 32580 | 543 | 22.625 | 105 | 1.75 | 0.072917 | 29895 | 498.25 | 20.7604
Work pipe from 1477.5 mbsf back to 1459.0 mbsf. Clear excess pump pressure and torque. Max top drive amps = 700. Max pump pressure = 3000 psi. | 19:30 | 2011-05-09 | 20:15 | 2011-05-09 | 45 | 0.75 | 0.03125 | 32625 | 543.75 | 22.6562 | 45 | 0.75 | 0.03125 | 29940 | 499 | 20.7917
RIH with the top drive and ream from 1477.6 to 1484.6 mbsf. Continue to RIH with the top drive to 1518.2 mbsf. | 20:15 | 2011-05-09 | 22:45 | 2011-05-09 | 150 | 2.5 | 0.10417 | 32775 | 546.25 | 22.7604 | 150 | 2.5 | 0.10417 | 30090 | 501.5 | 20.8958
Pump 150 bbls gel sweep at 1518.2 mbsf | 22:45 | 2011-05-09 | 1:00 | 2011-05-10 | 135 | 2.25 | 0.09375 | 32910 | 548.5 | 22.8542 | 135 | 2.25 | 0.09375 | 30225 | 503.75 | 20.9896
Pull back in the hole with the top drive from 1518.2 to 1324.6 mbsf | 1:00 | 2011-05-10 | 2:30 | 2011-05-10 | 90 | 1.5 | 0.0625 | 33000 | 550 | 22.9167 | 90 | 1.5 | 0.0625 | 30315 | 505.25 | 21.0521
Set back top drive | 2:30 | 2011-05-10 | 3:00 | 2011-05-10 | 30 | 0.5 | 0.020833 | 33030 | 550.5 | 22.9375 | 30 | 0.5 | 0.020833 | 30345 | 505.75 | 21.0729
Resume pulling back in the hole from 1324.6 to 78.2 mbsf | 3:00 | 2011-05-10 | 5:30 | 2011-05-10 | 150 | 2.5 | 0.10417 | 33180 | 553 | 23.0417 | 150 | 2.5 | 0.10417 | 30495 | 508.25 | 21.1771
Flush top of cone with seawater | 5:30 | 2011-05-10 | 5:45 | 2011-05-10 | 15 | 0.25 | 0.010417 | 33195 | 553.25 | 23.0521 | 15 | 0.25 | 0.010417 | 30510 | 508.5 | 21.1875
POOH with the drillstring from 78.2 mbsf. Clear sea floor at 0605 hr. Bit at rotary at 1130 hr | 5:45 | 2011-05-10 | 11:30 | 2011-05-10 | 345 | 5.75 | 0.23958 | 33540 | 559 | 23.2917 | 345 | 5.75 | 0.23958 | 30855 | 514.25 | 21.4271 | Clear seafloor at 06:05. End Run 11 at 11:30
Empty junk baskets, lay out tricone | 11:30 | 2011-05-10 | 12:15 | 2011-05-10 | 45 | 0.75 | 0.03125 | 33585 | 559.75 | 23.3229 | 45 | 0.75 | 0.03125 | 30900 | 515 | 21.4583 | nice cuttings in junk baskets. Samples Run11-EXJB
Make up Bowen reverse circulating junk basket, 1 junk basket, and 2 stands of drill collars and RIH to 2679 mbrf | 12:15 | 2011-05-10 | 19:30 | 2011-05-10 | 435 | 7.25 | 0.30208 | 34020 | 567 | 23.625 | 435 | 7.25 | 0.30208 | 31335 | 522.25 | 21.7604 | Start Run 12. Bowen reverse circulation junk basket
Slip and cut 115 feet of drilling line | 19:30 | 2011-05-10 | 21:00 | 2011-05-10 | 90 | 1.5 | 0.0625 | 34110 | 568.5 | 23.6875 | 90 | 1.5 | 0.0625 | 31425 | 523.75 | 21.8229
Install VIT | 21:00 | 2011-05-10 | 21:45 | 2011-05-10 | 45 | 0.75 | 0.03125 | 34155 | 569.25 | 23.7187 | 45 | 0.75 | 0.03125 | 31470 | 524.5 | 21.8542
Resume RIH with the drillstring from 2679 to 3640 mbrf | 21:45 | 2011-05-10 | 23:15 | 2011-05-10 | 90 | 1.5 | 0.0625 | 34245 | 570.75 | 23.7812 | 90 | 1.5 | 0.0625 | 31560 | 526 | 21.9167
Search and position vessel. Reenter Hole 1256D at 2330 hr (#12). | 23:15 | 2011-05-10 | 23:20 | 2011-05-10 | 5 | 0.083333 | 0.0034722 | 34250 | 570.8333 | 23.7847 | 5 | 0.083333 | 0.0034722 | 31565 | 526.0833 | 21.9201 | Reentry 12
RIH to 808.7 mbsf | 23:20 | 2011-05-10 | 1:00 | 2011-05-11 | 100 | 1.6667 | 0.069444 | 34350 | 572.5 | 23.8542 | 100 | 1.6667 | 0.069444 | 31665 | 527.75 | 21.9896
Recover VIT | 1:00 | 2011-05-11 | 1:30 | 2011-05-11 | 30 | 0.5 | 0.020833 | 34380 | 573 | 23.875 | 30 | 0.5 | 0.020833 | 31695 | 528.25 | 22.0104
Resume RIH from 808.7 to 1327.5 mbsf | 1:30 | 2011-05-11 | 2:30 | 2011-05-11 | 60 | 1 | 0.041667 | 34440 | 574 | 23.9167 | 60 | 1 | 0.041667 | 31755 | 529.25 | 22.0521
Pick up top drive | 2:30 | 2011-05-11 | 3:00 | 2011-05-11 | 30 | 0.5 | 0.020833 | 34470 | 574.5 | 23.9375 | 30 | 0.5 | 0.020833 | 31785 | 529.75 | 22.0729
Obtain slow circulating rate (SCR) parameters and RIH from 1327.5 to 1517.9 mbsf | 3:00 | 2011-05-11 | 6:30 | 2011-05-11 | 210 | 3.5 | 0.14583 | 34680 | 578 | 24.0833 | 210 | 3.5 | 0.14583 | 31995 | 533.25 | 22.2187
Clean hole. Circulate at 150 SPM with 1600 psi. Find 2.5 m of fill | 6:30 | 2011-05-11 | 8:30 | 2011-05-11 | 120 | 2 | 0.083333 | 34800 | 580 | 24.1667 | 120 | 2 | 0.083333 | 32115 | 535.25 | 22.3021
Pump 100 bbl hi-vis sweep and chase it with 1.5 drillstring volume of seawater | 8:30 | 2011-05-11 | 9:30 | 2011-05-11 | 60 | 1 | 0.041667 | 34860 | 581 | 24.2083 | 60 | 1 | 0.041667 | 32175 | 536.25 | 22.3437
Drop stainless steel ball at 0937 hr and activate reverse circulation in Bowen junk basket | 9:30 | 2011-05-11 | 10:00 | 2011-05-11 | 30 | 0.5 | 0.020833 | 34890 | 581.5 | 24.2292 | 30 | 0.5 | 0.020833 | 32205 | 536.75 | 22.3646 | Reverse circulation junk basket
Attempt to drill over junk at the bottom of the hole | 10:00 | 2011-05-11 | 10:30 | 2011-05-11 | 30 | 0.5 | 0.020833 | 34920 | 582 | 24.25 | 30 | 0.5 | 0.020833 | 32235 | 537.25 | 22.3854
Pull back in the hole from 1516.1 to 1328.6 mbsf | 10:30 | 2011-05-11 | 12:00 | 2011-05-11 | 90 | 1.5 | 0.0625 | 35010 | 583.5 | 24.3125 | 90 | 1.5 | 0.0625 | 32325 | 538.75 | 22.4479
Rack top drive | 12:00 | 2011-05-11 | 12:30 | 2011-05-11 | 30 | 0.5 | 0.020833 | 35040 | 584 | 24.3333 | 30 | 0.5 | 0.020833 | 32355 | 539.25 | 22.4687
POOH from 1328.6 mbsf to 58.9 mbrf. Clear top of cone at 1520 hr. | 12:30 | 2011-05-11 | 21:30 | 2011-05-11 | 540 | 9 | 0.375 | 35580 | 593 | 24.7083 | 540 | 9 | 0.375 | 32895 | 548.25 | 22.8437 | Clear seafloor at 15:20. End Run 12 at 22:00. Samples Run12-DC, Run12-EXJB, Run12-RCJB
Find BHA drill collars up to the TDC filled with fine cuttings (50 m) weighting on the order of several hundred kgs. Individually clear each drill collar and provide contents to scientists. Coarser gravel found in the head, crossover, and bit subs. Empty and clean out the Bowen tool containing about 20 kg of granoblastic dyke rocks. | 21:30 | 2011-05-11 | 5:30 | 2011-05-12 | 480 | 8 | 0.33333 | 36060 | 601 | 25.0417 | 480 | 8 | 0.33333 | 33375 | 556.25 | 23.1771 | big rock samples, no cone
Service rig | 5:30 | 2011-05-12 | 6:00 | 2011-05-12 | 30 | 0.5 | 0.020833 | 36090 | 601.5 | 25.0625 | 30 | 0.5 | 0.020833 | 33405 | 556.75 | 23.1979
Make up Bowen tool with single junk basket and 2 stands of drill collars and RIH to 2678 mbrf | 6:00 | 2011-05-12 | 11:30 | 2011-05-12 | 330 | 5.5 | 0.22917 | 36420 | 607 | 25.2917 | 330 | 5.5 | 0.22917 | 33735 | 562.25 | 23.4271 | Start Run 13. Bowen reverse circulation junk basket
Launch VIT | 11:30 | 2011-05-12 | 12:00 | 2011-05-12 | 30 | 0.5 | 0.020833 | 36450 | 607.5 | 25.3125 | 30 | 0.5 | 0.020833 | 33765 | 562.75 | 23.4479
Resume RIH from 2678 to 3631 mbrf | 12:00 | 2011-05-12 | 13:15 | 2011-05-12 | 75 | 1.25 | 0.052083 | 36525 | 608.75 | 25.3646 | 75 | 1.25 | 0.052083 | 33840 | 564 | 23.5
Search and position vessel. Reenter Hole 1256D at 1335 hr. | 13:15 | 2011-05-12 | 13:30 | 2011-05-12 | 15 | 0.25 | 0.010417 | 36540 | 609 | 25.375 | 15 | 0.25 | 0.010417 | 33855 | 564.25 | 23.5104 | Reentry 13
RIH with the drillpipe to 664.8 mbsf | 13:30 | 2011-05-12 | 15:00 | 2011-05-12 | 90 | 1.5 | 0.0625 | 36630 | 610.5 | 25.4375 | 90 | 1.5 | 0.0625 | 33945 | 565.75 | 23.5729
Recover VIT | 15:00 | 2011-05-12 | 15:30 | 2011-05-12 | 30 | 0.5 | 0.020833 | 36660 | 611 | 25.4583 | 30 | 0.5 | 0.020833 | 33975 | 566.25 | 23.5937
Resume RIH from 664.8 to 1384.8 mbsf | 15:30 | 2011-05-12 | 17:00 | 2011-05-12 | 90 | 1.5 | 0.0625 | 36750 | 612.5 | 25.5208 | 90 | 1.5 | 0.0625 | 34065 | 567.75 | 23.6562
Pick up top drive | 17:00 | 2011-05-12 | 17:30 | 2011-05-12 | 30 | 0.5 | 0.020833 | 36780 | 613 | 25.5417 | 30 | 0.5 | 0.020833 | 34095 | 568.25 | 23.6771
RIH with the top drive and rotation and circulation past a soft tag at 1465.0 mbsf and a hard tag at 1518.0 mbsf. Back flow on connections starting at 1470.0 mbsf. | 17:30 | 2011-05-12 | 20:15 | 2011-05-12 | 165 | 2.75 | 0.11458 | 36945 | 615.75 | 25.6562 | 165 | 2.75 | 0.11458 | 34260 | 571 | 23.7917
Work drilllstring to 1518.0 mbsf and fail in an attempt to penetrate to 1520.2 mbsf with max WOB = 2-4 Kips, and 160 spm at 1600 psi. TD current = 200-400 amps. Circulate 100 bbl hi-vis sweep. Chase same with 2X drillstring volume seawater. | 20:15 | 2011-05-12 | 22:15 | 2011-05-12 | 120 | 2 | 0.083333 | 37065 | 617.75 | 25.7396 | 120 | 2 | 0.083333 | 34380 | 573 | 23.875
Drop stainless ball to activate reverse circulation. Unable to shear pins in tool with pump pressure up to 3000 psi at 50 spm. | 22:15 | 2011-05-12 | 23:00 | 2011-05-12 | 45 | 0.75 | 0.03125 | 37110 | 618.5 | 25.7708 | 45 | 0.75 | 0.03125 | 34425 | 573.75 | 23.9062
Pull back in the hole with top drive to 1327.3 mbsf | 23:00 | 2011-05-12 | 0:45 | 2011-05-13 | 105 | 1.75 | 0.072917 | 37215 | 620.25 | 25.8437 | 105 | 1.75 | 0.072917 | 34530 | 575.5 | 23.9792
Rack top drive | 0:45 | 2011-05-13 | 1:15 | 2011-05-13 | 30 | 0.5 | 0.020833 | 37245 | 620.75 | 25.8646 | 30 | 0.5 | 0.020833 | 34560 | 576 | 24
POOH from 1327.3 mbsf and clear sea floor at 0340 hr. Bowen junk basket at rotary table at 1100 hr. Basket contains large granoblastic dyke rocks. The larger rock is 3.4 kgs. Apparently the Bowen tool was activated by the stainless ball. The loss of circulation was probably due to clogged jets. Almost the entire BHA was filled with fine cuttings again. | 1:15 | 2011-05-13 | 11:00 | 2011-05-13 | 585 | 9.75 | 0.40625 | 37830 | 630.5 | 26.2708 | 585 | 9.75 | 0.40625 | 35145 | 585.75 | 24.4062 | Clear seafloor at 03:40. End Run 13 at 11:00. Samples Run13-DC, Run13-EXJB, Run13-RCJB
Dismantle Bowen reverse circulating junk basket, clean all components and service | 11:00 | 2011-05-13 | 12:45 | 2011-05-13 | 105 | 1.75 | 0.072917 | 37935 | 632.25 | 26.3437 | 105 | 1.75 | 0.072917 | 35250 | 587.5 | 24.4792
Lay down Bowen tool and pick up Homco 9.75” flow through junk basket with bit sub junk basket and float, 2-stand BHA, and boot basket. Lay out 1 joint of 5 ½” of transition pipe. RIH to 2670 mbrf. | 12:45 | 2011-05-13 | 20:30 | 2011-05-13 | 465 | 7.75 | 0.32292 | 38400 | 640 | 26.6667 | 465 | 7.75 | 0.32292 | 35715 | 595.25 | 24.8021 | Start Run 14, Homco 9.75” flow through junk basket with bit sub junk basket and float.
Deploy VIT | 20:30 | 2011-05-13 | 21:15 | 2011-05-13 | 45 | 0.75 | 0.03125 | 38445 | 640.75 | 26.6979 | 45 | 0.75 | 0.03125 | 35760 | 596 | 24.8333
RIH with the drillpipe from 2670 to 3631 mbrf | 21:15 | 2011-05-13 | 23:00 | 2011-05-13 | 105 | 1.75 | 0.072917 | 38550 | 642.5 | 26.7708 | 105 | 1.75 | 0.072917 | 35865 | 597.75 | 24.9062
Search and position vessel. Reenter Hole 1256D at 2315 hr (#14) | 23:00 | 2011-05-13 | 23:15 | 2011-05-13 | 15 | 0.25 | 0.010417 | 38565 | 642.75 | 26.7812 | 15 | 0.25 | 0.010417 | 35880 | 598 | 24.9167 | Reentry 14
RIH with the drillstring to 512.1 mbsf | 23:15 | 2011-05-13 | 0:45 | 2011-05-14 | 90 | 1.5 | 0.0625 | 38655 | 644.25 | 26.8437 | 90 | 1.5 | 0.0625 | 35970 | 599.5 | 24.9792
Recover VIT | 0:45 | 2011-05-14 | 3:00 | 2011-05-14 | 135 | 2.25 | 0.09375 | 38790 | 646.5 | 26.9375 | 135 | 2.25 | 0.09375 | 36105 | 601.75 | 25.0729
Resume RIH from 512.1 to 1404.3 mbsf | 3:00 | 2011-05-14 | 3:30 | 2011-05-14 | 30 | 0.5 | 0.020833 | 38820 | 647 | 26.9583 | 30 | 0.5 | 0.020833 | 36135 | 602.25 | 25.0937
Continue to RIH from 1404.3 to 1517.2 mbsf | 3:30 | 2011-05-14 | 5:45 | 2011-05-14 | 135 | 2.25 | 0.09375 | 38955 | 649.25 | 27.0521 | 135 | 2.25 | 0.09375 | 36270 | 604.5 | 25.1875
Pump 100 bbl sweep and continue to work down to top of fish at 1521.0 mbsf | 5:45 | 2011-05-14 | 8:15 | 2011-05-14 | 150 | 2.5 | 0.10417 | 39105 | 651.75 | 27.1562 | 150 | 2.5 | 0.10417 | 36420 | 607 | 25.2917
Attempt to recover junk/fish | 8:15 | 2011-05-14 | 8:45 | 2011-05-14 | 30 | 0.5 | 0.020833 | 39135 | 652.25 | 27.1771 | 30 | 0.5 | 0.020833 | 36450 | 607.5 | 25.3125
Circulate 50 bbl sweep at 1520.0 mbsf | 8:45 | 2011-05-14 | 9:45 | 2011-05-14 | 60 | 1 | 0.041667 | 39195 | 653.25 | 27.2187 | 60 | 1 | 0.041667 | 36510 | 608.5 | 25.3542
Pull back in the hole with the top drive from 1519.2 to 1404.6 mbsf | 9:45 | 2011-05-14 | 10:30 | 2011-05-14 | 45 | 0.75 | 0.03125 | 39240 | 654 | 27.25 | 45 | 0.75 | 0.03125 | 36555 | 609.25 | 25.3854
Rack top drive | 10:30 | 2011-05-14 | 11:00 | 2011-05-14 | 30 | 0.5 | 0.020833 | 39270 | 654.5 | 27.2708 | 30 | 0.5 | 0.020833 | 36585 | 609.75 | 25.4062
POOH with the drillstring and clear seafloor at 1345 hr. Rack back drill collars in derrick. HOMCO FTJB clears rotary at 2010 hr. | 11:00 | 2011-05-14 | 20:15 | 2011-05-14 | 555 | 9.25 | 0.38542 | 39825 | 663.75 | 27.6562 | 555 | 9.25 | 0.38542 | 37140 | 619 | 25.7917 | clear seafloor at 13:45. End Run 14 at 20:10. Samples Run14-EXJB, BSJB, FTJB
Empty FTJB of two rocks (combined weight = 3.2 kgs). Lower set of junk catcher fingers completing torn out. | 20:15 | 2011-05-14 | 21:00 | 2011-05-14 | 45 | 0.75 | 0.03125 | 39870 | 664.5 | 27.6875 | 45 | 0.75 | 0.03125 | 37185 | 619.75 | 25.8229
Make up new Smith hard formation 9 7/8” tricone bit with single junk basket to 3-stand BHA and RIH to 84 mbrf | 21:00 | 2011-05-14 | 22:15 | 2011-05-14 | 75 | 1.25 | 0.052083 | 39945 | 665.75 | 27.7396 | 75 | 1.25 | 0.052083 | 37260 | 621 | 25.875 | Start Run 15, Smith hard formation 9 7/8” tricone bit with single junk basket
Slip and cut 115 feet of drilling line | 22:15 | 2011-05-14 | 23:45 | 2011-05-14 | 90 | 1.5 | 0.0625 | 40035 | 667.25 | 27.8021 | 90 | 1.5 | 0.0625 | 37350 | 622.5 | 25.9375
RIH with 5 ½” transition pipe to 132.9 mbrf | 23:45 | 2011-05-14 | 0:00 | 2011-05-15 | 15 | 0.25 | 0.010417 | 40050 | 667.5 | 27.8125 | 15 | 0.25 | 0.010417 | 37365 | 622.75 | 25.9479
Service rig | 0:00 | 2011-05-15 | 0:30 | 2011-05-15 | 30 | 0.5 | 0.020833 | 40080 | 668 | 27.8333 | 30 | 0.5 | 0.020833 | 37395 | 623.25 | 25.9687
Resume RIH with 5 ½” transition pipe from 133 to 2694 mbrf filling every 10 stands | 0:30 | 2011-05-15 | 5:00 | 2011-05-15 | 270 | 4.5 | 0.1875 | 40350 | 672.5 | 28.0208 | 270 | 4.5 | 0.1875 | 37665 | 627.75 | 26.1562
Deploy VIT | 5:00 | 2011-05-15 | 5:30 | 2011-05-15 | 30 | 0.5 | 0.020833 | 40380 | 673 | 28.0417 | 30 | 0.5 | 0.020833 | 37695 | 628.25 | 26.1771
Resume RIH from 2694 to 3924 mbrf. Reenter Hole 1256D (#15) at 0730 hr and RIH to 278.5 mbsf | 5:30 | 2011-05-15 | 8:30 | 2011-05-15 | 180 | 3 | 0.125 | 40560 | 676 | 28.1667 | 180 | 3 | 0.125 | 37875 | 631.25 | 26.3021 | Reentry 15
0830-0900 Recover VIT | 8:30 | 2011-05-15 | 9:00 | 2011-05-15 | 30 | 0.5 | 0.020833 | 40590 | 676.5 | 28.1875 | 30 | 0.5 | 0.020833 | 37905 | 631.75 | 26.3229
RIH from 278.5 to 1371.8 mbsf | 9:00 | 2011-05-15 | 12:15 | 2011-05-15 | 195 | 3.25 | 0.13542 | 40785 | 679.75 | 28.3229 | 195 | 3.25 | 0.13542 | 38100 | 635 | 26.4583
Pick up top drive | 12:15 | 2011-05-15 | 12:45 | 2011-05-15 | 30 | 0.5 | 0.020833 | 40815 | 680.25 | 28.3437 | 30 | 0.5 | 0.020833 | 38130 | 635.5 | 26.4792
Resume RIH from 1371.8 mbsf. Tag soft fill at 1510.0 mbsf and hard tag at 1518.8 mbsf | 12:45 | 2011-05-15 | 14:15 | 2011-05-15 | 90 | 1.5 | 0.0625 | 40905 | 681.75 | 28.4062 | 90 | 1.5 | 0.0625 | 38220 | 637 | 26.5417
Pick up 30-foot knobby and work bit with light WOB at 1518.5 mbsf and then down to 1520.6 mbsf multiple times attempting to stabilize the bottom 2-3 m of the hole. Hole packs off below 1518.0 mbsf and requires working back to bottom. Circulate multiple mud sweeps at 1520.6 mbsf (total bbls = 400 bbls). Continue to work drillstring from 1518.5 to 1521.05 mbsf. Pump 200 bbls of sweeps. Pull drillstring to inspect and change the bit. | 14:15 | 2011-05-15 | 6:15 | 2011-05-16 | 960 | 16 | 0.66667 | 41865 | 697.75 | 29.0729 | 960 | 16 | 0.66667 | 39180 | 653 | 27.2083
Pull back in the hole with the top drive from 1515.5 to 1410.1 mbsf | 6:15 | 2011-05-16 | 7:30 | 2011-05-16 | 75 | 1.25 | 0.052083 | 41940 | 699 | 29.125 | 75 | 1.25 | 0.052083 | 39255 | 654.25 | 27.2604
Rack top drive | 7:30 | 2011-05-16 | 8:00 | 2011-05-16 | 30 | 0.5 | 0.020833 | 41970 | 699.5 | 29.1458 | 30 | 0.5 | 0.020833 | 39285 | 654.75 | 27.2812
POOH with the drillstring and clear the seafloor at 1015 hr. Rack back 3 stands. Lay out . Bit clears rotary at 1545 hr. Inspect bit and find bearings still tight with virtually no wear exhibited on teeth except for a single chipped tooth on the heel. The bit is undergage by 0.4 inch with some shirttail wear and minor junk damage on the body. | 8:00 | 2011-05-16 | 15:45 | 2011-05-16 | 465 | 7.75 | 0.32292 | 42435 | 707.25 | 29.4687 | 465 | 7.75 | 0.32292 | 39750 | 662.5 | 27.6042 | clear seafloor at 10:15. End Run 15 at 15:45. Samples Run15-EXJB
Clean out junk basket | 15:45 | 2011-05-16 | 16:15 | 2011-05-16 | 30 | 0.5 | 0.020833 | 42465 | 707.75 | 29.4896 | 30 | 0.5 | 0.020833 | 39780 | 663 | 27.625
Make up new 9 7/8” Smith FH3VPS tricone to a 3-stand BHA and RIH to 2693 mbrf | 16:15 | 2011-05-16 | 0:00 | 2011-05-17 | 465 | 7.75 | 0.32292 | 42930 | 715.5 | 29.8125 | 465 | 7.75 | 0.32292 | 40245 | 670.75 | 27.9479 | Start Run 16, 9 7/8” Smith FH3VPS tricone
Deploy VIT | 0:00 | 2011-05-17 | 0:30 | 2011-05-17 | 30 | 0.5 | 0.020833 | 42960 | 716 | 29.8333 | 30 | 0.5 | 0.020833 | 40275 | 671.25 | 27.9687
Resume RIH from 2693 to 3644 mbrf | 0:30 | 2011-05-17 | 2:30 | 2011-05-17 | 120 | 2 | 0.083333 | 43080 | 718 | 29.9167 | 120 | 2 | 0.083333 | 40395 | 673.25 | 28.0521
Space out to reenter. Reenter Hole 1256D at 0245 hr for the 16th time of the expedition | 2:30 | 2011-05-17 | 2:45 | 2011-05-17 | 15 | 0.25 | 0.010417 | 43095 | 718.25 | 29.9271 | 15 | 0.25 | 0.010417 | 40410 | 673.5 | 28.0625 | Reentry 16
Resume RIH to 507.2 mbsf. Fill pipe every 10 stands | 2:45 | 2011-05-17 | 4:00 | 2011-05-17 | 75 | 1.25 | 0.052083 | 43170 | 719.5 | 29.9792 | 75 | 1.25 | 0.052083 | 40485 | 674.75 | 28.1146
Recover VIT | 4:00 | 2011-05-17 | 4:30 | 2011-05-17 | 30 | 0.5 | 0.020833 | 43200 | 720 | 30 | 30 | 0.5 | 0.020833 | 40515 | 675.25 | 28.1354
Continue to RIH from 507.2 to 1399.7 mbsf | 4:30 | 2011-05-17 | 6:30 | 2011-05-17 | 120 | 2 | 0.083333 | 43320 | 722 | 30.0833 | 120 | 2 | 0.083333 | 40635 | 677.25 | 28.2187
Pick up top drive | 6:30 | 2011-05-17 | 7:00 | 2011-05-17 | 30 | 0.5 | 0.020833 | 43350 | 722.5 | 30.1042 | 30 | 0.5 | 0.020833 | 40665 | 677.75 | 28.2396
RIH from 1399.7 to 1516.5 mbsf | 7:00 | 2011-05-17 | 8:15 | 2011-05-17 | 75 | 1.25 | 0.052083 | 43425 | 723.75 | 30.1562 | 75 | 1.25 | 0.052083 | 40740 | 679 | 28.2917
Wash and ream from 1516.5 to 1519.7 mbsf. Circulate 60 bbl sweep at 1516.7 mbsf. Flush hole with 200 bbls of mud at 1519.6 mbsf. | 8:15 | 2011-05-17 | 0:15 | 2011-05-18 | 960 | 16 | 0.66667 | 44385 | 739.75 | 30.8229 | 960 | 16 | 0.66667 | 41700 | 695 | 28.9583
Pull back in the hole with the top drive from 1519.6 to 1399.7 mbsf | 0:15 | 2011-05-18 | 1:00 | 2011-05-18 | 45 | 0.75 | 0.03125 | 44430 | 740.5 | 30.8542 | 45 | 0.75 | 0.03125 | 41745 | 695.75 | 28.9896
Rack top drive | 1:00 | 2011-05-18 | 1:30 | 2011-05-18 | 30 | 0.5 | 0.020833 | 44460 | 741 | 30.875 | 30 | 0.5 | 0.020833 | 41775 | 696.25 | 29.0104
POOH with the drillstring. Clear seafloor at 0340 hr. Bit at rotary table at 0900 hr. Lay out used tricone bit (in gage) and minus six teeth on one cone | 1:30 | 2011-05-18 | 9:00 | 2011-05-18 | 450 | 7.5 | 0.3125 | 44910 | 748.5 | 31.1875 | 450 | 7.5 | 0.3125 | 42225 | 703.75 | 29.3229 | clear seafloor at 03:40. End Run 16 at 09:00
Make up 9 5/8” flat-bottomed mill with EXJB and 3-stand BHA and RIH to 162 mbrf | 9:00 | 2011-05-18 | 10:30 | 2011-05-18 | 90 | 1.5 | 0.0625 | 45000 | 750 | 31.25 | 90 | 1.5 | 0.0625 | 42315 | 705.25 | 29.3854 | Start Run 17, 9 5/8” flat-bottomed mill with EXJB
Service rig | 10:30 | 2011-05-18 | 11:00 | 2011-05-18 | 30 | 0.5 | 0.020833 | 45030 | 750.5 | 31.2708 | 30 | 0.5 | 0.020833 | 42345 | 705.75 | 29.4062
Resume RIH from 162 to 2695 mbrf | 11:00 | 2011-05-18 | 15:45 | 2011-05-18 | 285 | 4.75 | 0.19792 | 45315 | 755.25 | 31.4687 | 285 | 4.75 | 0.19792 | 42630 | 710.5 | 29.6042
Install VIT | 15:45 | 2011-05-18 | 16:15 | 2011-05-18 | 30 | 0.5 | 0.020833 | 45345 | 755.75 | 31.4896 | 30 | 0.5 | 0.020833 | 42660 | 711 | 29.625
RIH from 2695 to 3637 mbrf | 16:15 | 2011-05-18 | 18:45 | 2011-05-18 | 150 | 2.5 | 0.10417 | 45495 | 758.25 | 31.5937 | 150 | 2.5 | 0.10417 | 42810 | 713.5 | 29.7292
Search and position vessel. Reenter Hole 1256D at 1850 hr | 18:45 | 2011-05-18 | 19:00 | 2011-05-18 | 15 | 0.25 | 0.010417 | 45510 | 758.5 | 31.6042 | 15 | 0.25 | 0.010417 | 42825 | 713.75 | 29.7396 | Reentry 17
RIH with the drillstring to 480.5 mbsf | 19:00 | 2011-05-18 | 20:15 | 2011-05-18 | 75 | 1.25 | 0.052083 | 45585 | 759.75 | 31.6562 | 75 | 1.25 | 0.052083 | 42900 | 715 | 29.7917
Recover VIT | 20:15 | 2011-05-18 | 20:45 | 2011-05-18 | 30 | 0.5 | 0.020833 | 45615 | 760.25 | 31.6771 | 30 | 0.5 | 0.020833 | 42930 | 715.5 | 29.8125
Resume RIH from 480.5 to 1429.9 mbsf | 20:45 | 2011-05-18 | 23:30 | 2011-05-18 | 165 | 2.75 | 0.11458 | 45780 | 763 | 31.7917 | 165 | 2.75 | 0.11458 | 43095 | 718.25 | 29.9271
Pick up top drive | 23:30 | 2011-05-18 | 0:00 | 2011-05-19 | 30 | 0.5 | 0.020833 | 45810 | 763.5 | 31.8125 | 30 | 0.5 | 0.020833 | 43125 | 718.75 | 29.9479
Continue to RIH with the top drive from 1429.9 to 1520.0 mbsf | 0:00 | 2011-05-19 | 1:30 | 2011-05-19 | 90 | 1.5 | 0.0625 | 45900 | 765 | 31.875 | 90 | 1.5 | 0.0625 | 43215 | 720.25 | 30.0104
Mill debris at 1520.0-1521.0 mbsf. Use junk basket pump sweeps. Pump 200 bbl sweep at 1520.0 mbsf | 1:30 | 2011-05-19 | 13:30 | 2011-05-19 | 720 | 12 | 0.5 | 46620 | 777 | 32.375 | 720 | 12 | 0.5 | 43935 | 732.25 | 30.5104
Circulate 100 bbl sweep and chase same with 2 X drillstring volume of seawater | 13:30 | 2011-05-19 | 14:45 | 2011-05-19 | 75 | 1.25 | 0.052083 | 46695 | 778.25 | 32.4271 | 75 | 1.25 | 0.052083 | 44010 | 733.5 | 30.5625
Lay out 30-foot knobby and pull back in the hole with the top drive to 1429.9 mbsf | 14:45 | 2011-05-19 | 15:30 | 2011-05-19 | 45 | 0.75 | 0.03125 | 46740 | 779 | 32.4583 | 45 | 0.75 | 0.03125 | 44055 | 734.25 | 30.5937
Rack top drive | 15:30 | 2011-05-19 | 16:00 | 2011-05-19 | 30 | 0.5 | 0.020833 | 46770 | 779.5 | 32.4792 | 30 | 0.5 | 0.020833 | 44085 | 734.75 | 30.6146
POOH and clear seafloor at 1920 hr. Offset vessel 50 m west and continue POOH to 2354 mbrf | 16:00 | 2011-05-19 | 21:30 | 2011-05-19 | 330 | 5.5 | 0.22917 | 47100 | 785 | 32.7083 | 330 | 5.5 | 0.22917 | 44415 | 740.25 | 30.8437 | clear seafloor at 19:20
Slip and cut 115 feet of drilling line | 21:30 | 2011-05-19 | 23:00 | 2011-05-19 | 90 | 1.5 | 0.0625 | 47190 | 786.5 | 32.7708 | 90 | 1.5 | 0.0625 | 44505 | 741.75 | 30.9062
Resume POOH to surface. Used mill at rotary table at 0315 hr. | 23:00 | 2011-05-19 | 3:15 | 2011-05-20 | 255 | 4.25 | 0.17708 | 47445 | 790.75 | 32.9479 | 255 | 4.25 | 0.17708 | 44760 | 746 | 31.0833 | End Run 17 at 03:15. Samples Run17-BSJB
Lay out mill. Clean and lay out damaged junk basket. Mill heavily worn and undergage by ~0.5.” Pick up new 9” flat mill with fresh junk basket and RIH to 162 mbrf. | 3:15 | 2011-05-20 | 5:30 | 2011-05-20 | 135 | 2.25 | 0.09375 | 47580 | 793 | 33.0417 | 135 | 2.25 | 0.09375 | 44895 | 748.25 | 31.1771 | Start Run 18, 9” flat mill with junk basket
Service rig | 5:30 | 2011-05-20 | 6:30 | 2011-05-20 | 60 | 1 | 0.041667 | 47640 | 794 | 33.0833 | 60 | 1 | 0.041667 | 44955 | 749.25 | 31.2187
Resume RIH from 162 to 2694 mbrf while filling every ten stands | 6:30 | 2011-05-20 | 11:30 | 2011-05-20 | 300 | 5 | 0.20833 | 47940 | 799 | 33.2917 | 300 | 5 | 0.20833 | 45255 | 754.25 | 31.4271
Launch VIT | 11:30 | 2011-05-20 | 12:00 | 2011-05-20 | 30 | 0.5 | 0.020833 | 47970 | 799.5 | 33.3125 | 30 | 0.5 | 0.020833 | 45285 | 754.75 | 31.4479
Resume RIH from 2694 to 3637 mbrf | 12:00 | 2011-05-20 | 13:45 | 2011-05-20 | 105 | 1.75 | 0.072917 | 48075 | 801.25 | 33.3854 | 105 | 1.75 | 0.072917 | 45390 | 756.5 | 31.5208
Search and position vessel. Reenter Hole 1256D for the 18th time at 1415 hr. | 13:45 | 2011-05-20 | 14:15 | 2011-05-20 | 30 | 0.5 | 0.020833 | 48105 | 801.75 | 33.4062 | 30 | 0.5 | 0.020833 | 45420 | 757 | 31.5417 | Reentry 18
RIH with the drillstring to 451.2 mbsf | 14:15 | 2011-05-20 | 15:30 | 2011-05-20 | 75 | 1.25 | 0.052083 | 48180 | 803 | 33.4583 | 75 | 1.25 | 0.052083 | 45495 | 758.25 | 31.5937
Recover VIT | 15:30 | 2011-05-20 | 16:00 | 2011-05-20 | 30 | 0.5 | 0.020833 | 48210 | 803.5 | 33.4792 | 30 | 0.5 | 0.020833 | 45525 | 758.75 | 31.6146
Resume RIH from 451.2 to 1458.6 mbsf | 16:00 | 2011-05-20 | 18:15 | 2011-05-20 | 135 | 2.25 | 0.09375 | 48345 | 805.75 | 33.5729 | 135 | 2.25 | 0.09375 | 45660 | 761 | 31.7083
Pick up top drive | 18:15 | 2011-05-20 | 18:45 | 2011-05-20 | 30 | 0.5 | 0.020833 | 48375 | 806.25 | 33.5937 | 30 | 0.5 | 0.020833 | 45690 | 761.5 | 31.7292
RIH with the top drive and tag fill at 1518.9 mbsf. Advance with low pump and rotary speed and tag hard fill at 1520.4 mbsf. | 18:45 | 2011-05-20 | 19:45 | 2011-05-20 | 60 | 1 | 0.041667 | 48435 | 807.25 | 33.6354 | 60 | 1 | 0.041667 | 45750 | 762.5 | 31.7708
Mill junk and work junk basket. Pump 100 bbl sepiolite sweep; Pump 120bl sweep at 1520.9mbsf | 19:45 | 2011-05-20 | 1:45 | 2011-05-21 | 360 | 6 | 0.25 | 48795 | 813.25 | 33.8854 | 360 | 6 | 0.25 | 46110 | 768.5 | 32.0208
Pump 100 bbl sepiolite sweep and circulate out | 1:45 | 2011-05-21 | 3:00 | 2011-05-21 | 75 | 1.25 | 0.052083 | 48870 | 814.5 | 33.9375 | 75 | 1.25 | 0.052083 | 46185 | 769.75 | 32.0729
Pull back in the hole with the top drive from 1520.9 to 1429.8 mbsf. | 3:00 | 2011-05-21 | 4:00 | 2011-05-21 | 60 | 1 | 0.041667 | 48930 | 815.5 | 33.9792 | 60 | 1 | 0.041667 | 46245 | 770.75 | 32.1146
Rack top drive | 4:00 | 2011-05-21 | 4:30 | 2011-05-21 | 30 | 0.5 | 0.020833 | 48960 | 816 | 34 | 30 | 0.5 | 0.020833 | 46275 | 771.25 | 32.1354
POOH from 1520.9 mbsf and clear the seafloor at 0645 hr. The milling tool was at the drill floor at 1225 hr. The abrasive surface of the milling tool was eroded away and some external junk damage noted on the side of the tool and the crossover sub directly above the mill. | 4:30 | 2011-05-21 | 12:30 | 2011-05-21 | 480 | 8 | 0.33333 | 49440 | 824 | 34.3333 | 480 | 8 | 0.33333 | 46755 | 779.25 | 32.4687 | clear seafloor at 06:45
Empty and clean out the external junk basket. In addition to the usual rock fragments and fine cuttings, some flakes of what appears to be freshly ground metal also found. | 12:30 | 2011-05-21 | 12:45 | 2011-05-21 | 15 | 0.25 | 0.010417 | 49455 | 824.25 | 34.3437 | 15 | 0.25 | 0.010417 | 46770 | 779.5 | 32.4792 | End Run 18 at 12:25. Samples Run18-BSJB
Make up reverse circulating junk basket (RCJB) with three external junk baskets (EXJB) and deploy along with a 2-stand BHA. RIH to 2670 mbrf. | 12:45 | 2011-05-21 | 20:15 | 2011-05-21 | 450 | 7.5 | 0.3125 | 49905 | 831.75 | 34.6562 | 450 | 7.5 | 0.3125 | 47220 | 787 | 32.7917 | Start Run 19, Reverse circulation JB + 3 external JB's
Install VIT | 20:15 | 2011-05-21 | 20:45 | 2011-05-21 | 30 | 0.5 | 0.020833 | 49935 | 832.25 | 34.6771 | 30 | 0.5 | 0.020833 | 47250 | 787.5 | 32.8125
RIH with the drillstring to 3632 mbrf | 20:45 | 2011-05-21 | 22:15 | 2011-05-21 | 90 | 1.5 | 0.0625 | 50025 | 833.75 | 34.7396 | 90 | 1.5 | 0.0625 | 47340 | 789 | 32.875
Search and position vessel. Reenter Hole 1256D for the 19th time at 2230 hr. | 22:15 | 2011-05-21 | 22:30 | 2011-05-21 | 15 | 0.25 | 0.010417 | 50040 | 834 | 34.75 | 15 | 0.25 | 0.010417 | 47355 | 789.25 | 32.8854 | Reentry 19
RIH with the drillpipe to 599.6 mbsf | 22:30 | 2011-05-21 | 23:45 | 2011-05-21 | 75 | 1.25 | 0.052083 | 50115 | 835.25 | 34.8021 | 75 | 1.25 | 0.052083 | 47430 | 790.5 | 32.9375
Recover VIT | 23:45 | 2011-05-21 | 0:15 | 2011-05-22 | 30 | 0.5 | 0.020833 | 50145 | 835.75 | 34.8229 | 30 | 0.5 | 0.020833 | 47460 | 791 | 32.9583
Continue to RIH from 599.6 to 1405.7 mbsf | 0:15 | 2011-05-22 | 1:30 | 2011-05-22 | 75 | 1.25 | 0.052083 | 50220 | 837 | 34.875 | 75 | 1.25 | 0.052083 | 47535 | 792.25 | 33.0104
Pick up top drive | 1:30 | 2011-05-22 | 2:00 | 2011-05-22 | 30 | 0.5 | 0.020833 | 50250 | 837.5 | 34.8958 | 30 | 0.5 | 0.020833 | 47565 | 792.75 | 33.0312
RIH from 1405.7 to 1519.5 mbsf. Hard tag at 1519.5 mbsf | 2:00 | 2011-05-22 | 3:15 | 2011-05-22 | 75 | 1.25 | 0.052083 | 50325 | 838.75 | 34.9479 | 75 | 1.25 | 0.052083 | 47640 | 794 | 33.0833
Work junk baskets | 3:15 | 2011-05-22 | 3:45 | 2011-05-22 | 30 | 0.5 | 0.020833 | 50355 | 839.25 | 34.9687 | 30 | 0.5 | 0.020833 | 47670 | 794.5 | 33.1042
Pump 100 barrel sweep and chase same with 2X annular volume. Continue to work junk baskets | 3:45 | 2011-05-22 | 5:45 | 2011-05-22 | 120 | 2 | 0.083333 | 50475 | 841.25 | 35.0521 | 120 | 2 | 0.083333 | 47790 | 796.5 | 33.1875
Drop stainless steel activation ball in open pipe. Advance RCJB down to 1520.5 mbsf with slow rotation and light weight on bit. Jog rotation attempting to catch debris. | 5:45 | 2011-05-22 | 7:00 | 2011-05-22 | 75 | 1.25 | 0.052083 | 50550 | 842.5 | 35.1042 | 75 | 1.25 | 0.052083 | 47865 | 797.75 | 33.2396
Pull back in the hole with the top drive from 1520.5 to 1434.4 mbsf | 7:00 | 2011-05-22 | 7:30 | 2011-05-22 | 30 | 0.5 | 0.020833 | 50580 | 843 | 35.125 | 30 | 0.5 | 0.020833 | 47895 | 798.25 | 33.2604
Rack top drive | 7:30 | 2011-05-22 | 8:00 | 2011-05-22 | 30 | 0.5 | 0.020833 | 50610 | 843.5 | 35.1458 | 30 | 0.5 | 0.020833 | 47925 | 798.75 | 33.2812
POOH with the drillstring and clear seafloor at 1015 hr. Rack back BHA. RCJB at rotary table at 1645 hr. | 8:00 | 2011-05-22 | 16:45 | 2011-05-22 | 525 | 8.75 | 0.36458 | 51135 | 852.25 | 35.5104 | 525 | 8.75 | 0.36458 | 48450 | 807.5 | 33.6458 | clear seafloor at 10:15
Empty RCJB of congealed sepiolite and 4 large rocks with total weight = 8.9 Kg. Largest rock weight = 3.9 Kg. Unload 3 EXJB of cuttings and a few small metal fragments. | 16:45 | 2011-05-22 | 18:00 | 2011-05-22 | 75 | 1.25 | 0.052083 | 51210 | 853.5 | 35.5625 | 75 | 1.25 | 0.052083 | 48525 | 808.75 | 33.6979 | End Run 19 at 16:45. Samples Run19-RCJB, BSJB and EXBJ
Rebuild and make up RCJB and 3 EXJB with a 2-stand BHA and RIH to 1793 mbrf | 18:00 | 2011-05-22 | 0:00 | 2011-05-23 | 360 | 6 | 0.25 | 51570 | 859.5 | 35.8125 | 360 | 6 | 0.25 | 48885 | 814.75 | 33.9479 | Start Run 20, Reverse circulation JB + 3 external JB's
Repair pneumatic supply lines for drawworks high clutch | 0:00 | 2011-05-23 | 3:00 | 2011-05-23 | 180 | 3 | 0.125 | 51750 | 862.5 | 35.9375 | 180 | 3 | 0.125 | 49065 | 817.75 | 34.0729
Resume RIH from 1793 to 2670 mbrf | 3:00 | 2011-05-23 | 4:15 | 2011-05-23 | 75 | 1.25 | 0.052083 | 51825 | 863.75 | 35.9896 | 75 | 1.25 | 0.052083 | 49140 | 819 | 34.125
Launch VIT | 4:15 | 2011-05-23 | 4:45 | 2011-05-23 | 30 | 0.5 | 0.020833 | 51855 | 864.25 | 36.0104 | 30 | 0.5 | 0.020833 | 49170 | 819.5 | 34.1458
RIH from 2670 to 3640 mbrf | 4:45 | 2011-05-23 | 6:30 | 2011-05-23 | 105 | 1.75 | 0.072917 | 51960 | 866 | 36.0833 | 105 | 1.75 | 0.072917 | 49275 | 821.25 | 34.2188
Position vessel, space out, and reenter Hole 1256D at 0635 hr | 6:30 | 2011-05-23 | 6:45 | 2011-05-23 | 15 | 0.25 | 0.010417 | 51975 | 866.25 | 36.0938 | 15 | 0.25 | 0.010417 | 49290 | 821.5 | 34.2292 | Reentry 20
RIH to 513.5 mbsf | 6:45 | 2011-05-23 | 7:30 | 2011-05-23 | 45 | 0.75 | 0.03125 | 52020 | 867 | 36.125 | 45 | 0.75 | 0.03125 | 49335 | 822.25 | 34.2604
Recover VIT | 7:30 | 2011-05-23 | 8:00 | 2011-05-23 | 30 | 0.5 | 0.020833 | 52050 | 867.5 | 36.1458 | 30 | 0.5 | 0.020833 | 49365 | 822.75 | 34.2812
Resume RIH from 513.5 to 1462.9 mbsf | 8:00 | 2011-05-23 | 9:15 | 2011-05-23 | 75 | 1.25 | 0.052083 | 52125 | 868.75 | 36.1979 | 75 | 1.25 | 0.052083 | 49440 | 824 | 34.3333
Pick up top drive | 9:15 | 2011-05-23 | 9:45 | 2011-05-23 | 30 | 0.5 | 0.020833 | 52155 | 869.25 | 36.2188 | 30 | 0.5 | 0.020833 | 49470 | 824.5 | 34.3542
Continue to RIH from 1462.9 to 1519.0 mbsf | 9:45 | 2011-05-23 | 10:30 | 2011-05-23 | 45 | 0.75 | 0.03125 | 52200 | 870 | 36.25 | 45 | 0.75 | 0.03125 | 49515 | 825.25 | 34.3854
Hard tag at 1519.5 mbsf (tide adjusted). Work external junk baskets | 10:30 | 2011-05-23 | 10:45 | 2011-05-23 | 15 | 0.25 | 0.010417 | 52215 | 870.25 | 36.2604 | 15 | 0.25 | 0.010417 | 49530 | 825.5 | 34.3958
Pump 100 barrel sweep followed by 2X annular volume seawater | 10:45 | 2011-05-23 | 12:30 | 2011-05-23 | 105 | 1.75 | 0.072917 | 52320 | 872 | 36.3333 | 105 | 1.75 | 0.072917 | 49635 | 827.25 | 34.4688
Drop ball and activate RCJB. Note increase in pressure of 600 psi. Unable to pass hard tag at 1519.0 mbsf with max weight on bit = 7 Kips with very slow rotation. | 12:30 | 2011-05-23 | 13:15 | 2011-05-23 | 45 | 0.75 | 0.03125 | 52365 | 872.75 | 36.3646 | 45 | 0.75 | 0.03125 | 49680 | 828 | 34.5
Pull back in the hole with the top drive to 1462.9 mbsf | 13:15 | 2011-05-23 | 14:00 | 2011-05-23 | 45 | 0.75 | 0.03125 | 52410 | 873.5 | 36.3958 | 45 | 0.75 | 0.03125 | 49725 | 828.75 | 34.5312
Rack top drive | 14:00 | 2011-05-23 | 14:30 | 2011-05-23 | 30 | 0.5 | 0.020833 | 52440 | 874 | 36.4167 | 30 | 0.5 | 0.020833 | 49755 | 829.25 | 34.5521
POOH with the drillstring to 3042 mbrf. Clear seafloor at 1725 hr. | 14:30 | 2011-05-23 | 18:30 | 2011-05-23 | 240 | 4 | 0.16667 | 52680 | 878 | 36.5833 | 240 | 4 | 0.16667 | 49995 | 833.25 | 34.7188 | clear seafloor at 17:25
Slit and cut 115 feet of drilling line | 18:30 | 2011-05-23 | 20:00 | 2011-05-23 | 90 | 1.5 | 0.0625 | 52770 | 879.5 | 36.6458 | 90 | 1.5 | 0.0625 | 50085 | 834.75 | 34.7812
Resume POOH from 3042 to surface. RCJB at the rotary table at 0215 hr. | 20:00 | 2011-05-23 | 2:15 | 2011-05-24 | 375 | 6.25 | 0.26042 | 53145 | 885.75 | 36.9062 | 375 | 6.25 | 0.26042 | 50460 | 841 | 35.0417
Layout and empty RCJB and 3 EXJB. The RCJB contains 3 rocks with a total weight = 5.0 Kg. One rock (1.4 Kg) is gabbro. The angularity of the rocks indicates that they were freshly deposited with a suspected origin somewhere in the bottom 7 m of the hole. The external junk baskets contain gravel sized cuttings to small pebbles. | 2:15 | 2011-05-24 | 5:00 | 2011-05-24 | 165 | 2.75 | 0.11458 | 53310 | 888.5 | 37.0208 | 165 | 2.75 | 0.11458 | 50625 | 843.75 | 35.1562 | End Run 20 at 02:15. Samples Run20-RCJB, BSJB, and EXJB
Make up RCJB and 3 EXJB with 2-stand BHA and RIH to 131 mbrf | 5:00 | 2011-05-24 | 5:45 | 2011-05-24 | 45 | 0.75 | 0.03125 | 53355 | 889.25 | 37.0521 | 45 | 0.75 | 0.03125 | 50670 | 844.5 | 35.1875 | Start Run 21, Reverse circulation JB + 3 external JB's
Service rig | 5:45 | 2011-05-24 | 6:15 | 2011-05-24 | 30 | 0.5 | 0.020833 | 53385 | 889.75 | 37.0729 | 30 | 0.5 | 0.020833 | 50700 | 845 | 35.2083
Continue to RIH from 131 to 2670 mbrf | 6:15 | 2011-05-24 | 9:30 | 2011-05-24 | 195 | 3.25 | 0.13542 | 53580 | 893 | 37.2083 | 195 | 3.25 | 0.13542 | 50895 | 848.25 | 35.3438
Launch VIT | 9:30 | 2011-05-24 | 10:00 | 2011-05-24 | 30 | 0.5 | 0.020833 | 53610 | 893.5 | 37.2292 | 30 | 0.5 | 0.020833 | 50925 | 848.75 | 35.3646
Resume RIH from 2670 to 3640.0 mbrf. Reenter Hole 1256D at 1115 hr for the 21st time of the expedition | 10:00 | 2011-05-24 | 11:15 | 2011-05-24 | 75 | 1.25 | 0.052083 | 53685 | 894.75 | 37.2813 | 75 | 1.25 | 0.052083 | 51000 | 850 | 35.4167 | Reentry 21
Continue to RIH to 340.9 mbsf | 11:15 | 2011-05-24 | 12:00 | 2011-05-24 | 45 | 0.75 | 0.03125 | 53730 | 895.5 | 37.3125 | 45 | 0.75 | 0.03125 | 51045 | 850.75 | 35.4479
Recover VIT | 12:00 | 2011-05-24 | 12:30 | 2011-05-24 | 30 | 0.5 | 0.020833 | 53760 | 896 | 37.3333 | 30 | 0.5 | 0.020833 | 51075 | 851.25 | 35.4688
Resume RIH from 340.9 to 1434.4 mbsf | 12:30 | 2011-05-24 | 14:45 | 2011-05-24 | 135 | 2.25 | 0.09375 | 53895 | 898.25 | 37.4271 | 135 | 2.25 | 0.09375 | 51210 | 853.5 | 35.5625
Pick up top drive | 14:45 | 2011-05-24 | 15:15 | 2011-05-24 | 30 | 0.5 | 0.020833 | 53925 | 898.75 | 37.4479 | 30 | 0.5 | 0.020833 | 51240 | 854 | 35.5833
RIH with the top drive and minimum pump/rotation. Tag soft fill at 1518.8 mbsf. | 15:15 | 2011-05-24 | 16:15 | 2011-05-24 | 60 | 1 | 0.041667 | 53985 | 899.75 | 37.4896 | 60 | 1 | 0.041667 | 51300 | 855 | 35.625
Wash down to 1519.8 mbsf and work junk baskets | 16:15 | 2011-05-24 | 16:30 | 2011-05-24 | 15 | 0.25 | 0.010417 | 54000 | 900 | 37.5 | 15 | 0.25 | 0.010417 | 51315 | 855.25 | 35.6354
Pump 100 bbls of sepiolite sweep mud and chase with 2X annular volume of seawater | 16:30 | 2011-05-24 | 18:00 | 2011-05-24 | 90 | 1.5 | 0.0625 | 54090 | 901.5 | 37.5625 | 90 | 1.5 | 0.0625 | 51405 | 856.75 | 35.6979
Drop ball, activate RCJB, and work same | 18:00 | 2011-05-24 | 18:45 | 2011-05-24 | 45 | 0.75 | 0.03125 | 54135 | 902.25 | 37.5938 | 45 | 0.75 | 0.03125 | 51450 | 857.5 | 35.7292
Displace lower portion of annulus with 200 bbls of drill water in preparation for logging | 18:45 | 2011-05-24 | 19:30 | 2011-05-24 | 45 | 0.75 | 0.03125 | 54180 | 903 | 37.625 | 45 | 0.75 | 0.03125 | 51495 | 858.25 | 35.7604
Pull back in the hole with the top drive to 1462.9 mbsf | 19:30 | 2011-05-24 | 20:00 | 2011-05-24 | 30 | 0.5 | 0.020833 | 54210 | 903.5 | 37.6458 | 30 | 0.5 | 0.020833 | 51525 | 858.75 | 35.7813
Rack top drive | 20:00 | 2011-05-24 | 20:30 | 2011-05-24 | 30 | 0.5 | 0.020833 | 54240 | 904 | 37.6667 | 30 | 0.5 | 0.020833 | 51555 | 859.25 | 35.8021
Pull back in the hole with the drillstring to 53.2 mbsf | 20:30 | 2011-05-24 | 0:00 | 2011-05-25 | 210 | 3.5 | 0.14583 | 54450 | 907.5 | 37.8125 | 210 | 3.5 | 0.14583 | 51765 | 862.75 | 35.9479
Repair and replace damaged cam roller on DES | 0:00 | 2011-05-25 | 1:00 | 2011-05-25 | 60 | 1 | 0.041667 | 54510 | 908.5 | 37.8542 | 60 | 1 | 0.041667 | 51825 | 863.75 | 35.9896
Resume POOH from 53.2 mbsf and clear seafloor at 0100 hr | 1:00 | 2011-05-25 | 7:00 | 2011-05-25 | 360 | 6 | 0.25 | 54870 | 914.5 | 38.1042 | 360 | 6 | 0.25 | 52185 | 869.75 | 36.2396 | clear seafloor at 01:00
Disassemble and empty RCJB of 4 small cobbles. Empty 3 EXJBs and clean out same of the usual assortment of cuttings etc | 7:00 | 2011-05-25 | 8:15 | 2011-05-25 | 75 | 1.25 | 0.052083 | 54945 | 915.75 | 38.1563 | 75 | 1.25 | 0.052083 | 52260 | 871 | 36.2917 | End Run 21 at 07:00. Samples Run21-RCJB, BSJB, and EXJB
Make up Bowen fishing magnet (FM) and 3 EXJBs and RIH to 109.5 mbrf | 8:15 | 2011-05-25 | 9:30 | 2011-05-25 | 75 | 1.25 | 0.052083 | 55020 | 917 | 38.2083 | 75 | 1.25 | 0.052083 | 52335 | 872.25 | 36.3438 | Start Run 22, Fishing magnet + 3 JB's
Service rig | 9:30 | 2011-05-25 | 10:00 | 2011-05-25 | 30 | 0.5 | 0.020833 | 55050 | 917.5 | 38.2292 | 30 | 0.5 | 0.020833 | 52365 | 872.75 | 36.3646
Resume RIH from 109.5 to 2612 mbrf | 10:00 | 2011-05-25 | 14:30 | 2011-05-25 | 270 | 4.5 | 0.1875 | 55320 | 922 | 38.4167 | 270 | 4.5 | 0.1875 | 52635 | 877.25 | 36.5521
Install VIT | 14:30 | 2011-05-25 | 15:00 | 2011-05-25 | 30 | 0.5 | 0.020833 | 55350 | 922.5 | 38.4375 | 30 | 0.5 | 0.020833 | 52665 | 877.75 | 36.5729
Continue to RIH from 2612 to 3632 mbrf | 15:00 | 2011-05-25 | 16:30 | 2011-05-25 | 90 | 1.5 | 0.0625 | 55440 | 924 | 38.5 | 90 | 1.5 | 0.0625 | 52755 | 879.25 | 36.6354
Search and position vessel. Reenter Hole 1245D at 1645 hr (#22). | 16:30 | 2011-05-25 | 16:45 | 2011-05-25 | 15 | 0.25 | 0.010417 | 55455 | 924.25 | 38.5104 | 15 | 0.25 | 0.010417 | 52770 | 879.5 | 36.6458 | Reentry 22
RIH to 427.1 mbsf | 16:45 | 2011-05-25 | 18:00 | 2011-05-25 | 75 | 1.25 | 0.052083 | 55530 | 925.5 | 38.5625 | 75 | 1.25 | 0.052083 | 52845 | 880.75 | 36.6979
Recover VIT | 18:00 | 2011-05-25 | 18:30 | 2011-05-25 | 30 | 0.5 | 0.020833 | 55560 | 926 | 38.5833 | 30 | 0.5 | 0.020833 | 52875 | 881.25 | 36.7188
Resume RIH from 427.1 to 1462.6 mbsf | 18:30 | 2011-05-25 | 21:00 | 2011-05-25 | 150 | 2.5 | 0.10417 | 55710 | 928.5 | 38.6875 | 150 | 2.5 | 0.10417 | 53025 | 883.75 | 36.8229
Pick up top drive | 21:00 | 2011-05-25 | 21:30 | 2011-05-25 | 30 | 0.5 | 0.020833 | 55740 | 929 | 38.7083 | 30 | 0.5 | 0.020833 | 53055 | 884.25 | 36.8438
RIH with the top drive. Tag fill at 1519.0 mbsf. | 21:30 | 2011-05-25 | 22:00 | 2011-05-25 | 30 | 0.5 | 0.020833 | 55770 | 929.5 | 38.7292 | 30 | 0.5 | 0.020833 | 53085 | 884.75 | 36.8646
Wash down to 1520.0 mbsf. Work fishing magnet and junk baskets. | 22:00 | 2011-05-25 | 22:30 | 2011-05-25 | 30 | 0.5 | 0.020833 | 55800 | 930 | 38.75 | 30 | 0.5 | 0.020833 | 53115 | 885.25 | 36.8854
Displace lower annulus with 200 bbls of drill water | 22:30 | 2011-05-25 | 23:00 | 2011-05-25 | 30 | 0.5 | 0.020833 | 55830 | 930.5 | 38.7708 | 30 | 0.5 | 0.020833 | 53145 | 885.75 | 36.9063
Pull back with the top drive to 1433.8 mbsf | 23:00 | 2011-05-25 | 23:45 | 2011-05-25 | 45 | 0.75 | 0.03125 | 55875 | 931.25 | 38.8021 | 45 | 0.75 | 0.03125 | 53190 | 886.5 | 36.9375
Rack top drive | 23:45 | 2011-05-25 | 0:15 | 2011-05-26 | 30 | 0.5 | 0.020833 | 55905 | 931.75 | 38.8229 | 30 | 0.5 | 0.020833 | 53220 | 887 | 36.9583
POOH with the drillstring and clear seafloor at 0230 hr | 0:15 | 2011-05-26 | 8:00 | 2011-05-26 | 465 | 7.75 | 0.32292 | 56370 | 939.5 | 39.1458 | 465 | 7.75 | 0.32292 | 53685 | 894.75 | 37.2813 | clear seafloor at 02:30
Disassemble and empty EXJBs. Fishing magnet contained very little metal debris all of which was finely ground!??! | 8:00 | 2011-05-26 | 9:00 | 2011-05-26 | 60 | 1 | 0.041667 | 56430 | 940.5 | 39.1875 | 60 | 1 | 0.041667 | 53745 | 895.75 | 37.3229 | End Run 22 at 08:00. Samples Run22-FM, BSJB, and EXJB
Make up and deploy logging bit and collars and deploy same to 2923 mbrf | 9:00 | 2011-05-26 | 15:30 | 2011-05-26 | 390 | 6.5 | 0.27083 | 56820 | 947 | 39.4583 | 390 | 6.5 | 0.27083 | 54135 | 902.25 | 37.5938 | Start Run 23, downhole measurements (logging bit)
Deploy VIT | 15:30 | 2011-05-26 | 16:00 | 2011-05-26 | 30 | 0.5 | 0.020833 | 56850 | 947.5 | 39.4792 | 30 | 0.5 | 0.020833 | 54165 | 902.75 | 37.6146
RIH with the drillstring to 3638 mbrf | 16:00 | 2011-05-26 | 17:15 | 2011-05-26 | 75 | 1.25 | 0.052083 | 56925 | 948.75 | 39.5313 | 75 | 1.25 | 0.052083 | 54240 | 904 | 37.6667
Search and position vessel. Reenter Hole 1256D at 1725 hr. | 17:15 | 2011-05-26 | 17:30 | 2011-05-26 | 15 | 0.25 | 0.010417 | 56940 | 949 | 39.5417 | 15 | 0.25 | 0.010417 | 54255 | 904.25 | 37.6771 | Reentry 23
RIH with the drillstring to 203.3 mbsf. Pick up 2 knobbies and set EOP at 218.9 mbsf. | 17:30 | 2011-05-26 | 18:45 | 2011-05-26 | 75 | 1.25 | 0.052083 | 57015 | 950.25 | 39.5938 | 75 | 1.25 | 0.052083 | 54330 | 905.5 | 37.7292
Recover VIT | 18:45 | 2011-05-26 | 20:00 | 2011-05-26 | 75 | 1.25 | 0.052083 | 57090 | 951.5 | 39.6458 | 75 | 1.25 | 0.052083 | 54405 | 906.75 | 37.7813
Rig up for logging | 20:00 | 2011-05-26 | 20:30 | 2011-05-26 | 30 | 0.5 | 0.020833 | 57120 | 952 | 39.6667 | 30 | 0.5 | 0.020833 | 54435 | 907.25 | 37.8021
Make up Log #1 (Triple combo-GR/APS/HLDS/HRLA/GPIT) | 20:30 | 2011-05-26 | 23:00 | 2011-05-26 | 150 | 2.5 | 0.10417 | 57270 | 954.5 | 39.7708 | 150 | 2.5 | 0.10417 | 54585 | 909.75 | 37.9063
Deploy Log #1 into the pipe at 2255 hr. Reached the bottom of the hole at 1520.0 mbsf. Recover tool at 0700 hr. | 23:00 | 2011-05-26 | 7:00 | 2011-05-27 | 480 | 8 | 0.33333 | 57750 | 962.5 | 40.1042 | 480 | 8 | 0.33333 | 55065 | 917.75 | 38.2396
Disassemble Triple combo. Make up 2nd log (Formation Microscanner with sonic tool). Deploy FMS-sonic into the pipe at 1050 hr | 7:00 | 2011-05-27 | 11:00 | 2011-05-27 | 240 | 4 | 0.16667 | 57990 | 966.5 | 40.2708 | 240 | 4 | 0.16667 | 55305 | 921.75 | 38.4063
Tool unable to exit pipe into hole. Recover FMS-sonic at 1410 hr | 11:00 | 2011-05-27 | 14:15 | 2011-05-27 | 195 | 3.25 | 0.13542 | 58185 | 969.75 | 40.4063 | 195 | 3.25 | 0.13542 | 55500 | 925 | 38.5417
Replace damaged lower centralizer spring and redeploy FMS-sonic at 1500 hr | 14:15 | 2011-05-27 | 15:00 | 2011-05-27 | 45 | 0.75 | 0.03125 | 58230 | 970.5 | 40.4375 | 45 | 0.75 | 0.03125 | 55545 | 925.75 | 38.5729
Run in with the FMS-sonic. Tool appears to jam inside BHA with lower section (~20m) of unit extending 20m into the open hole | 15:00 | 2011-05-27 | 16:30 | 2011-05-27 | 90 | 1.5 | 0.0625 | 58320 | 972 | 40.5 | 90 | 1.5 | 0.0625 | 55635 | 927.25 | 38.6354 | FMS-sonic string jammed in logging bit
Attempt to pump tool clear without success | 16:30 | 2011-05-27 | 18:15 | 2011-05-27 | 105 | 1.75 | 0.072917 | 58425 | 973.75 | 40.5729 | 105 | 1.75 | 0.072917 | 55740 | 929 | 38.7083
Make up Kinley Cutter assemblies. Drop crimper into pipe at 2135 hr | 18:15 | 2011-05-27 | 22:45 | 2011-05-27 | 270 | 4.5 | 0.1875 | 58695 | 978.25 | 40.7604 | 270 | 4.5 | 0.1875 | 56010 | 933.5 | 38.8958
Drop hammer into pipe at 2245 hr | 22:45 | 2011-05-27 | 23:15 | 2011-05-27 | 30 | 0.5 | 0.020833 | 58725 | 978.75 | 40.7813 | 30 | 0.5 | 0.020833 | 56040 | 934 | 38.9167
Assemble Kinley severing tool and drop into pipe | 23:15 | 2011-05-27 | 1:15 | 2011-05-28 | 120 | 2 | 0.083333 | 58845 | 980.75 | 40.8646 | 120 | 2 | 0.083333 | 56160 | 936 | 39
Drop hammer and server logging cable | 1:15 | 2011-05-28 | 1:45 | 2011-05-28 | 30 | 0.5 | 0.020833 | 58875 | 981.25 | 40.8854 | 30 | 0.5 | 0.020833 | 56190 | 936.5 | 39.0208
Recover and tie back logging cable | 1:45 | 2011-05-28 | 3:30 | 2011-05-28 | 105 | 1.75 | 0.072917 | 58980 | 983 | 40.9583 | 105 | 1.75 | 0.072917 | 56295 | 938.25 | 39.0938
POOH with the drillstring to 19 mbrf. Clear seafloor at 0425 hr. | 3:30 | 2011-05-28 | 9:30 | 2011-05-28 | 360 | 6 | 0.25 | 59340 | 989 | 41.2083 | 360 | 6 | 0.25 | 56655 | 944.25 | 39.3438 | clea seafloor at 04:25
Release jammed FMS-sonic tool from landing saver sub in BHA. Tool is in good condition. | 9:30 | 2011-05-28 | 12:00 | 2011-05-28 | 150 | 2.5 | 0.10417 | 59490 | 991.5 | 41.3125 | 150 | 2.5 | 0.10417 | 56805 | 946.75 | 39.4479 | End Run 23 at 09:30. No FMS, no UBI
Make up RCB 3-stand BHA with new RCB C-9 bit. Check core barrel space out and RIH to 134 mbrf | 12:00 | 2011-05-28 | 14:00 | 2011-05-28 | 120 | 2 | 0.083333 | 59610 | 993.5 | 41.3958 | 120 | 2 | 0.083333 | 56925 | 948.75 | 39.5313 | Start Run 24, Ulterra RCB-9 bit for coring and then cementing
Slip and cut 115 feet of drilling line (#8 of expedition) | 14:00 | 2011-05-28 | 15:30 | 2011-05-28 | 90 | 1.5 | 0.0625 | 59700 | 995 | 41.4583 | 90 | 1.5 | 0.0625 | 57015 | 950.25 | 39.5938
RIH with the drillstring to 2695 mbrf | 15:30 | 2011-05-28 | 20:30 | 2011-05-28 | 300 | 5 | 0.20833 | 60000 | 1000 | 41.6667 | 300 | 5 | 0.20833 | 57315 | 955.25 | 39.8021
Launch VIT | 20:30 | 2011-05-28 | 21:00 | 2011-05-28 | 30 | 0.5 | 0.020833 | 60030 | 1000.5 | 41.6875 | 30 | 0.5 | 0.020833 | 57345 | 955.75 | 39.8229
RIH with the drillstring to 3638 mbrf | 21:00 | 2011-05-28 | 22:15 | 2011-05-28 | 75 | 1.25 | 0.052083 | 60105 | 1001.75 | 41.7396 | 75 | 1.25 | 0.052083 | 57420 | 957 | 39.875
Search and position vessel. Reenter Hole 1256D at 2225 hr for the 24th time of the expedition | 22:15 | 2011-05-28 | 22:30 | 2011-05-28 | 15 | 0.25 | 0.010417 | 60120 | 1002 | 41.75 | 15 | 0.25 | 0.010417 | 57435 | 957.25 | 39.8854 | Reentry 24
RIH with the drillstring to 1430.5 mbsf | 22:30 | 2011-05-28 | 1:15 | 2011-05-29 | 165 | 2.75 | 0.11458 | 60285 | 1004.75 | 41.8646 | 165 | 2.75 | 0.11458 | 57600 | 960 | 40
Recover VIT and coat line on the way out | 1:15 | 2011-05-29 | 2:00 | 2011-05-29 | 45 | 0.75 | 0.03125 | 60330 | 1005.5 | 41.8958 | 45 | 0.75 | 0.03125 | 57645 | 960.75 | 40.0313
Pick up top drive and obtain slow circulating rate parameters | 2:00 | 2011-05-29 | 2:30 | 2011-05-29 | 30 | 0.5 | 0.020833 | 60360 | 1006 | 41.9167 | 30 | 0.5 | 0.020833 | 57675 | 961.25 | 40.0521
RIH with the top drive from 1430.5 to 1520.2 mbsf | 2:30 | 2011-05-29 | 4:00 | 2011-05-29 | 90 | 1.5 | 0.0625 | 60450 | 1007.5 | 41.9792 | 90 | 1.5 | 0.0625 | 57765 | 962.75 | 40.1146
Circulate 100 bbl sweep at 1520.0 mbsf | 4:00 | 2011-05-29 | 5:15 | 2011-05-29 | 75 | 1.25 | 0.052083 | 60525 | 1008.75 | 42.0313 | 75 | 1.25 | 0.052083 | 57840 | 964 | 40.1667
Drop fresh core barrel and rotary core 1256D-239R (1520.2 to 1521.6 mbsf) at an average rate of penetration = 0.6 m/hr. The average recovery = 36%. No indication of metal in the core barrel. No symptoms of downhole junk in the coring process. Time for coring expires. Prepare for cementing. Circulate 50 bbl sweep at 1521.6 mbsf. | 5:15 | 2011-05-29 | 10:15 | 2011-05-29 | 300 | 5 | 0.20833 | 60825 | 1013.75 | 42.2396 | 300 | 5 | 0.20833 | 58140 | 969 | 40.375 | core 239R
RIH with the coring line to 1510.6 mbsf and coat same on retrieval | 10:15 | 2011-05-29 | 12:00 | 2011-05-29 | 105 | 1.75 | 0.072917 | 60930 | 1015.5 | 42.3125 | 105 | 1.75 | 0.072917 | 58245 | 970.75 | 40.4479
Rack sinker bars and dress for layup period | 12:00 | 2011-05-29 | 12:15 | 2011-05-29 | 15 | 0.25 | 0.010417 | 60945 | 1015.75 | 42.3229 | 15 | 0.25 | 0.010417 | 58260 | 971 | 40.4583
Pull back in the hole with the top drive to 1487.8 mbsf. Rack top drive | 12:15 | 2011-05-29 | 13:15 | 2011-05-29 | 60 | 1 | 0.041667 | 61005 | 1016.75 | 42.3646 | 60 | 1 | 0.041667 | 58320 | 972 | 40.5
Make up circulating head and pressure test same. Position bit at 1518.6 mbsf | 13:15 | 2011-05-29 | 13:45 | 2011-05-29 | 30 | 0.5 | 0.020833 | 61035 | 1017.25 | 42.3854 | 30 | 0.5 | 0.020833 | 58350 | 972.5 | 40.5208
Mix and pump 15 bbls of 15 ppg cement | 13:45 | 2011-05-29 | 14:15 | 2011-05-29 | 30 | 0.5 | 0.020833 | 61065 | 1017.75 | 42.4063 | 30 | 0.5 | 0.020833 | 58380 | 973 | 40.5417 | Cement plug 1 (BOH)
Displace cement with seawater | 14:15 | 2011-05-29 | 14:45 | 2011-05-29 | 30 | 0.5 | 0.020833 | 61095 | 1018.25 | 42.4271 | 30 | 0.5 | 0.020833 | 58410 | 973.5 | 40.5625
Layout circulating head and pull back in the hole to 1372.6 mbsf | 14:45 | 2011-05-29 | 15:15 | 2011-05-29 | 30 | 0.5 | 0.020833 | 61125 | 1018.75 | 42.4479 | 30 | 0.5 | 0.020833 | 58440 | 974 | 40.5833
Flush drillstring with 2X annular volumes of seawater | 15:15 | 2011-05-29 | 16:15 | 2011-05-29 | 60 | 1 | 0.041667 | 61185 | 1019.75 | 42.4896 | 60 | 1 | 0.041667 | 58500 | 975 | 40.625
Pull back with the drillstring to 940.8 mbsf | 16:15 | 2011-05-29 | 17:15 | 2011-05-29 | 60 | 1 | 0.041667 | 61245 | 1020.75 | 42.5313 | 60 | 1 | 0.041667 | 58560 | 976 | 40.6667
Mix and pump 58 bbls of 15 ppg cement slurry | 17:15 | 2011-05-29 | 18:15 | 2011-05-29 | 60 | 1 | 0.041667 | 61305 | 1021.75 | 42.5729 | 60 | 1 | 0.041667 | 58620 | 977 | 40.7083 | Cement plug 2 (910-940 mbsf)
Displace cement with seawater | 18:15 | 2011-05-29 | 18:45 | 2011-05-29 | 30 | 0.5 | 0.020833 | 61335 | 1022.25 | 42.5938 | 30 | 0.5 | 0.020833 | 58650 | 977.5 | 40.7292
Pull back with the drillstring to 739.3 mbsf | 18:45 | 2011-05-29 | 19:30 | 2011-05-29 | 45 | 0.75 | 0.03125 | 61380 | 1023 | 42.625 | 45 | 0.75 | 0.03125 | 58695 | 978.25 | 40.7604
Flush drillstring with 2X annular volumes of seawater | 19:30 | 2011-05-29 | 20:00 | 2011-05-29 | 30 | 0.5 | 0.020833 | 61410 | 1023.5 | 42.6458 | 30 | 0.5 | 0.020833 | 58725 | 978.75 | 40.7813
POOH with the drillstring. Clear top of cone at 2135 hr. Disassemble BHA and stow drill collars in forward tubular racks. | 20:00 | 2011-05-29 | 8:00 | 2011-05-30 | 720 | 12 | 0.5 | 62130 | 1035.5 | 43.1458 | 720 | 12 | 0.5 | 59445 | 990.75 | 41.2813 | clear seafloor at 21:35. End Run 24
Recover beacons and secure vessel for sea | 8:00 | 2011-05-30 | 11:30 | 2011-05-30 | 210 | 3.5 | 0.14583 | 62340 | 1039 | 43.2917 | 210 | 3.5 | 0.14583 | 59655 | 994.25 | 41.4271
Underway to Balboa, Panama. Advance clock one hour on May 31 (12:00) | 11:30 | 2011-05-30 | 7:00 | 2011-06-03 | 5490 | 91.5 | 3.8125 | 67830 | 1130.5 | 47.1042 | [6 empty] | End of Expedition 335

## pipe trips
Summary of pipe trips
Water depth | 3645
| depth bsf | pipe trip total | pipe trip total cumulative |  | date start | comment
| (m) | (m) | (km) | (miles)
Trip 1 | 925 | 9140 | 9.14 | 5.6793 | 2011-04-19 | tricone bit (Smith 9 7/8” F9 tricone bit ), work obstruction @ 922
Trip 2 | 923 | 9136 | 18.276 | 11.3562 | 2011-04-21 | tricone bit (Reed 9 7/8” tricone bit, IADC Type 517) + Boot Baskets, work obstruction @ 922.
Trip 3 | 922 | 9134 | 27.41 | 17.0318 | 2011-04-23 | BHA with used Reed tricone bit without jets, cementing (5 bbls)
Trip 4 | 922 | 9134 | 36.544 | 22.7074 | 2011-04-24 | tricone bit (9 7/8” tricone bit, Atlas HP61), work obstruction @ 922
Trip 5 | 922 | 9134 | 45.678 | 28.383 | 2011-04-25 | BHA with used Reed tricone bit without jets, cementing (50 bbls)
Trip 6 | 923 | 9136 | 54.814 | 34.0598 | 2011-04-26 | tricone bit (9 7/8” Atlas HP61) + Boot Baskets, work obstruction @ 922.
Trip 7 | 1507 | 10304 | 65.118 | 40.4624 | 2011-04-28 | tricone bit (Smith 9 7/8”), work obstruction @ 922. Succeeded on April 29
Trip 8 | 960 | 9210 | 74.328 | 46.1853 | 2011-05-02 | BHA with used Reed tricone bit without jets, cementing the 920-940 trouble zone (60 bbls)
Trip 9 | 1520 | 10330 | 84.658 | 52.604 | 3-May | RCB assembly with RBI/9 7/8” RCB C-9, at bottom on May 4, coring, disintegrated bit
Trip 10 | 1434 | 10158 | 94.816 | 58.9159 | 2011-05-07 | 9” Bowen fishing magnet, circulation lost, 4m of cuttings in bit sub.
Trip 11 | 1520 | 10330 | 105.146 | 65.3347 | 2011-05-08 | tricone (Atlas 9 7/8” HP61) with 2 junk baskets, large cuttings in JB.
Trip 12 | 1518 | 10326 | 115.472 | 71.751 | 2011-05-10 | Bowen 9.75” reverse circulation junk basket, ~2.5 m of fill, activated on May 11, BHA filled with ~50 m of fine cuttings, large rock samples in RCJB.
Trip 13 | 1518 | 10326 | 125.798 | 78.1673 | 2011-05-12 | Bowen 9.75” reverse circulation junk basket, ~2 m of fill, activated on May 12, circulation lost.
Trip 14 | 1520 | 10330 | 136.128 | 84.586 | 2011-05-13 | Homco 9.75” flow through junk basket with bit sub junk basket and float
Trip 15 | 1520 | 10330 | 146.458 | 91.0048 | 2011-05-14 | Smith hard formation 9 7/8” 7JS tricone bit with single junk basket
Trip 16 | 1520 | 10330 | 156.788 | 97.4235 | 2011-05-16 | 9 7/8” Smith FH3VPS tricone
Trip 17 | 1520 | 10330 | 167.118 | 103.8423 | 2011-05-18 | 9 5/8” flat-bottomed mill with bitsub junk basket
Trip 18 | 1520 | 10330 | 177.448 | 110.2611 | 2011-05-20 | 9” flat mill with fresh junk basket
Trip 19 | 1520 | 10330 | 187.778 | 116.6798 | 2011-05-21 | reverse circulating junk basket (RCJB) with three external junk baskets
Trip 20 | 1520 | 10330 | 198.108 | 123.0986 | 2011-05-22 | reverse circulating junk basket (RCJB) with three external junk baskets
Trip 21 | 1520 | 10330 | 208.438 | 129.5174 | 2011-05-24 | reverse circulating junk basket (RCJB) with three external junk baskets
Trip 22 | 1520 | 10330 | 218.768 | 135.9361 | 2011-05-25 | 9” Bowen fishing magnet, with three external junk baskets
Trip 23 | 218 | 7726 | 226.494 | 140.7368 | 2011-05-26 | Logging (triple combo, FMS, and UBI)
Trip 24 | 1522 | 10334 | 236.828 | 147.1581 | 2011-05-28 | Ulterra RCB C-9 bit

## Operation-sampling summary
Operation and sampling summary, Expedition 335
Run # | Maximum depth (mbsf) | Cumulative pipe trip (km) | Date (2011) | Local time (start, hrs) | Duration (days) | Tools | Samples | Comments
1 | 925 | 9.14 | 2011-04-19 | 1:15 | 2.6042 | tricone bit Smith 9 7/8” F9 |  | work obstruction @ ~922 mbsf
2 | 923 | 18.276 | 2011-04-21 | 15:45 | 1.6354 | tricone bit Reed 9 7/8”, IADC Type 517; external junk baskets | Run02-EXJB | work obstruction @ ~922 mbsf
3 | 922 | 27.41 | 2011-04-23 | 7:00 | 0.92708 | Used Reed tricone bit without jets |  | cementing (5 bbls)
4 | 922 | 36.544 | 2011-04-24 | 5:15 | 1.0417 | tricone bit 9 7/8” Atlas HP61 |  | work obstruction @ ~922 mbsf
5 | 922 | 45.678 | 2011-04-25 | 6:15 | 0.89583 | Used Reed tricone bit without jets |  | cementing (50 bbls)
6 | 923 | 54.814 | 2011-04-26 | 3:45 | 2.4688 | tricone bit 9 7/8” Atlas HP61; external junk baskets | Run06-EXJB | work obstruction @ ~922 mbsf
7 | 1507.1 | 65.118 | 2011-04-28 | 15:00 | 3.4896 | tricone bit Smith 9 7/8” |  | work obstruction @ ~922 mbsf; cleared on April 29; Hole open to bottom on May 1, 09:00
8 | 960.5 | 74.328 | 2011-05-02 | 2:45 | 1.0208 | Used Reed tricone bit without jets |  | cementing the 920-940 trouble zone (60 bbls)
9 | 1507.1 | 84.658 | 2011-05-03 | 3:15 | 1.9375 | RCB assembly with RBI/9 7/8” RCB C-9 | Ghost cores 1G to 6G; wash core 7W | cores mostly empty, except for a few pebbles of cement. At bottom on May 4
9 | 1516.5 |  | 2011-05-05 | 1:45 | 0.48264 | no liner, non-magnetic core barrel | 235R ; 236R | 0.33 m recovered, 7%; 0.61 m recovered, 13%
9 | 1520.2 |  | 2011-05-05 | 13:20 | 1.684 | no liner, non-magnetic core barrel | 237R; 238R | 0 m recovered; 0.20 m recovered, 10%. Core catcher damaged, bit destroyed
10 | 1434 | 94.816 | 2011-05-07 | 5:45 | 1.4271 | 9” Bowen fishing magnet; external junk baskets | Run10-DC, EXJB, and FM | Lost circulation; 4 m of fine cuttings plugging inside bit sub and two junk baskets
11 | 1520 | 105.146 | 2011-05-08 | 16:00 | 1.8438 | tricone (Atlas 9 7/8” HP61); external junk baskets | Run11-DC and EXJB | large cuttings in JB
12 | 1518 | 115.472 | 2011-05-10 | 12:15 | 1.7396 | Bowen 9.75” reverse circulation junk basket | Run12-DC, EXJB, and RCJB | ~2.5 m of fill. BHA filled with ~50 m of fine cuttings, large rock samples (total ~20 kg) in RCJB
13 | 1518 | 125.798 | 2011-05-12 | 6:00 | 1.2812 | Bowen 9.75” reverse circulation junk basket | Run13-DC, EXJB, and RCJB | ~2 m of fill, ~entire BHA filled with sand, large rock samples (largest ~3.4 kg) in RCJB
14 | 1520.2 | 136.13 | 2011-05-13 | 12:45 | 1.3438 | Homco 9.75” flow through junk basket; bit sub junk basket and float | Run14-FTJB, EXJB, and BSJB | 2 cobbles (total ~ 3.2 kg) in FTJB
15 | 1520.2 | 146.462 | 2011-05-14 | 21:00 | 1.8021 | Smith hard formation 9 7/8” 7JS tricone bit; single junk basket | Run15-EXJB | rock fragments and fine cuttings
16 | 1520.2 | 156.792 | 2011-05-16 | 16:15 | 1.7604 | 9 7/8” Smith FH3VPS tricone
17 | 1520.2 | 167.124 | 2011-05-18 | 10:30 | 1.6979 | 9 5/8” flat-bottomed mill; bitsub junk basket | Run16-BSJB | rock fragments and fine cuttings
18 | 1520.2 | 177.456 | 2011-05-20 | 3:15 | 1.3958 | 9” flat mill with; bitsub junk basket | Run18-BSJB | rock fragments and fine cuttings
19 | 1520.2 | 187.788 | 2011-05-21 | 12:45 | 1.2188 | reverse circulating junk basket; three external junk baskets (BSJB + 2 EXJB) | Run19-RCJB, BSJB, and EXJB | 4 large rocks in RCJB (total ~8.9 kg; largest ~3.9 kg); gravel sized cuttings to small pebbles in EXJB and BSJB
20 | 1520.2 | 198.12 | 2011-05-22 | 18:00 | 1.4583 | reverse circulating junk basket; three external junk baskets (BSJB + 2 EXJB) | Run20-RCJB, BSJB, and EXJB | 3 rocks in RCJB (total ~5.0 kg), 1 is gabbro (1.4 kg); gravel sized cuttings to small pebbles in EXJB and BSJB
21 | 1520.2 | 208.452 | 2011-05-24 | 5:00 | 1.1354 | reverse circulating junk basket; three external junk baskets (BSJB + 2 EXJB) | Run21-RCJB, BSJB, and EXJB | 4 small cobbles in RCJB; gravel sized cuttings to small pebbles in EXJB and BSJB
22 | 1520.2 | 218.784 | 2011-05-25 | 8:15 | 1.0312 | 9” Bowen fishing magnet; three external junk baskets (BSJB + 2 EXJB) | Run22-BSJB and EXJB | Fishing Magnet clear, very little metal debris. Rock fragments and fine cuttings in EXJB and BSJB
23 | 218 | 226.51 | 2011-05-26 | 9:00 | 2.125 | Logging (triple combo, FMS, and UBI) |  | FMS-sonic stuck in logging bit. Only triple combo run
24 | 1521.6 | 236.826 | 2011-05-28 | 12:00 | 1.8333 | Ulterra RCB-9 coring bit | 239R | 0.5 m recovered, 35.7%. Cementing bottom (15 bbls), and 910-940 mbsf zone (50 bbls). Lay out BHA.
|  |  | 2011-05-30 | 8:00

## brief summary
Summary of operations on IODP Expedition 335
Phase 1 | Open hole to full depth, cement to stabilize hole (920-960 mbsf) | 15 days (9 reentries)
Phase 2 | Core (4 cores, 8 % recovery); Coring bit destroyed | ~ 2 day (1 reentry)
Phase 3 | Fish/mill junk, ream/clean hole | 19 days (13 reentries)
Phase 4 | Logging | ~ 2 days (1 reentry)
Phase 5 | Core (1 core, 35% recovery), cement to stabilize hole (BOH to 1510, 940-910 mbsf) | ~ 1.5 days (1 reentry)
• 24 reentries, ~150 miles (~240 km) of pipe trip
• 920-940 mbsf zone : stabilized (15 trips through after cementing end of Phase 1 without any trouble)
• Hole : clean & clear of cuttings, no metal junk left at bottom
• Cone : clear
• "Fieldwork" samples from ocean crust thermal boundary layer