## Sheet1
Instrument tests
No. of test | Time | Location | Tool | Check | Remarks
1 | 01/29/2018 07:39 | Middle pipe rack | Borehole cable (DMC) | strainmeter health check after carrying to middle pipe rack
2 | 01/29/2018 16:20 | Moonpool | Borehole cable (DMC) | instrument condition before lowering LTBMS into the water | Loose wire connection of the USB-RS-422 Moxa adaptor; inadequate power supply from the CMG-Stream server; PC screens showing difficulites in adjusting brightness
3 | 01/30/2018 00:49 | Moonpool | Borehole cable (DMC) | LTBMS condition at 100 mbsf
4 | 01/30/2018 13:07 | Moonpool | Borehole cable (DMC) | Instrument condition before swellable packer installation
5 | 01/30/2018 15:50 | Moonpool | Borehole cable (DMC) | Instrument condition after swellable packer installation
6 | 01/30/2018 23:34 | Moonpool | Borehole cable (DMC) | Instrument condition/connection ability before cutting of the borehole cable
7 | 01/31/2018 02:33 | Moonpool | Borehole cable (DMC) | Instrument condition/connection immediately after cutting the sensor cables
8 | 01/31/2018 14:25 | Moonpool | Borehole cable (UMC) | Instrument condition/connection ability after soldering of the wires
9 | 01/31/2018 17:21 | Moonpool | Borehole cable (UMC) | Instrument condition/connection ability after the final epoxy (resin) pour
10 | 01/31/2018 22:10 | Moonpool | Borehole cable (UMC) | Instrument condition/connection ability after the sensor cables were spliced midway through UMC termination
11 | 02/01/2018 00:32 | Moonpool | Borehole cable (UMC) | Instrument condition/connection ability after teminating of the FACT, before attachement of the senosr cable to the CORK HEAD
12 | 02/01/2018 05:00 | Moonpool | Borehole cable (UMC) | Instrument condition/connection ability (including PSU) after attachement of the sensor cable to the CORK HEAD | CMG downlink was not possible due to a faulty cable. Therefore the borehole cable was cut and a spare fact was reconnected to the borehole cable.
13 | 02/01/2018 14:10 | Moonpool | Borehole cable (DMC) | CMG instrument condition after removing the UMC (with potential problems) | CMG stand-alone test via direct connection between sensor cable and test equipment, without FACT
14 | 02/01/2018 23:40 | Moonpool | Borehole cable (UMC) | CMG instrument condition/communication ability after soldering of wires, before epoxy hardening
15 | 02/02/2018 05:13 | Moonpool | Borehole cable (UMC) | CMG instrument condition/communication ability after epoxy hardening
16 | 02/02/2018 07:52 | Moonpool | Borehole cable (UMC) | Instrument condition/connection ability after reterminating of the CMG FACT, before attachement to the CORK HEAD
17 | 02/02/2018 09:14 | Moonpool | Borehole cable (UMC) | Instrument condition/connection ability after reattachment of the cable to the CORK HEAD | All sensor's communication, including tilt combo, strainmeter, and CMG, were comfirmed.
18 | 02/02/2018 11:43 | Moonpool | Acoustic modem | Instrument health before deployment
19 | 02/03/2018 00:35 | Sonar room | Acoustic modem | Instrument/LTBMS condition at 1400mbsf
20 | 02/03/2018 07:55 | Sonar room | Acoustic modem | Instrument/LTBMS condition at 3880 mbsf (before Reentry)
21 | 02/03/2018 16:14 | Sonar room | Acoustic modem | Instrument/LTBMS condition after landing
22 | 02/03/2018 18:49 | Sonar room | Acoustic modem | Monitoring of instrument health/temperature during cementing procedure | Only strainmeter was checked for monitoring of pressure and temperature data during the cementing procedure
23 | 02/04/2018 05:54 | Sonar room | Acoustic modem | Instrument condition after cementing (before releasing)
24 | 02/05/2018 06:54 | Sonar room | Acoustic modem | Instrument condition after releasing